## Start Here
From: LeanTakt team
Download the free PDF

## Takt Elements
Project Name
2024 | [52 empty] | 2025
Cold Winter Months | [43 empty] | Cold Winter Months | [51 empty] | Cold Winter Months
JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
 | time axis 2024-01-01 to 2025-12-29
INTERIORS LEGEND
[43 empty] | SOIL DISTURBANCE PERMIT | [29 empty] | 1 | Wall Layout + Top Track
[46 empty] | MAKE SAFE UTILITIES | [26 empty] | 2 | Fire Sprinkler + Priority Walls
[48 empty] | MOBILIZATION | [24 empty] | 3 | OH Ductwork
[50 empty] | EXCAVATION | [5 empty] | BIM LEGEND | [16 empty] | 4 | OH Branch Conduits and Lighting
[51 empty] | SHORING | [5 empty] | Model Coordination | [15 empty] | 5 | OH Mechanical Piping
[53 empty] | PIERS |  |  |  | Prepare Shop Drawings + Layout Drawings | [15 empty] | 6 | OH Electrical
[57 empty] | Shop Drawing Approval | [15 empty] | 7 | Wall Framing
[42 empty] | UG BIM Coordination | [14 empty] | Prefabrication of Material | [15 empty] | 8 | In wall Rough-in
[73 empty] | 9 | Soffits + Ceilings
[39 empty] | Shaft Prep | [33 empty] | 10 | Soffit & Ceiling Rough
[43 empty] | Elevator Cabs | [29 empty] | 11 | Drywall
[57 empty] | Test + Certification | [15 empty] | 12 | Taping
[39 empty] | Erect Stair | [33 empty] | 13 | Prime + First Coat
[43 empty] | Pour Stair Pans | [29 empty] | 14 | Data Cabling
[73 empty] | 15 | Ceiling Grid
[41 empty] | Temp Roof |  |  |  |  | Install Swing Stages | [26 empty] | 16 | Casework + Doors
[50 empty] | Set AHU & Install | [22 empty] | 17 | MEP Trim / Light and Devices
[55 empty] | Roofing | [17 empty] | 18 | Flooring + Baseboards
[73 empty] | 19 | Final Paint
[73 empty] | 20 | Final Accessories
[46 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | [5 empty] | 21 | Pre-Punch & Clean
[73 empty] | 22 | Punchlist
More colors
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | B | 15 | 16 | PI
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 |  |  |  |  | B |  |  |  | 13 | 14 | IR | B | 16 | PI
[12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[14 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
[16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
[17 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[38 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[39 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[40 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[41 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  |  | 13 13 13 12 11 10 9 8 7: A; 13 13 13 13 12 11 10 9 8: B; 13 13 13 13 13 12 11 10 9: C; 13 13 13 13 13 13 12 11 10: D; 13 13 13 13 13 13 13 12 11: E; 13 13 13 13 13 13 13 13 12: F
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | 13 13 13 13 12 11 10 9 8: A; 13 13 13 13 13 12 11 10 9: B; 13 13 13 13 13 13 12 11 10: C; 13 13 13 13 13 13 13 12 11: D; 13 13 13 13 13 13 13 13 12: E; 13 13 13 13 13 13 13 13 13: F
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 13 13 13 13 13 12 11 10 9: A; 13 13 13 13 13 13 12 11 10: B; 13 13 13 13 13 13 13 12 11: C; 13 13 13 13 13 13 13 13 12: D; 13 13 13 13 13 13 13 13 13: E | F
[12 empty] | 1 | 2 | 3 | 4 | 5 | 9 8 7 6 5 4 3 2 1: 6; 13 13 13 13 13 13 12 11 10: A; 13 13 13 13 13 13 13 12 11: B; 13 13 13 13 13 13 13 13 12: C; 13 13 13 13 13 13 13 13 13: D | E | F
[13 empty] | 1 | 2 | 3 | 4 | 9 8 7 6 5 4 3 2 1: 5; 10 9 8 7 6 5 4 3 2: 6; 13 13 13 13 13 13 13 12 11: A; 13 13 13 13 13 13 13 13 12: B; 13 13 13 13 13 13 13 13 13: C | D | E | F
[14 empty] | 1 | 2 | 3 | 9 8 7 6 5 4 3 2 1: 4; 10 9 8 7 6 5 4 3 2: 5; 11 10 9 8 7 6 5 4 3: 6; 13 13 13 13 13 13 13 13 12: A; 13 13 13 13 13 13 13 13 13: B | C | D | E | F
Interiors
Finishes
Logistics Map
LEVEL 3
LEVEL 2
LEVEL 1
TARGET SUBSTANTIAL COMPLETION
POWER ON
AC ON
4 Week Look Ahead
Color palettes You can copy these colors for your takt's format
Examples of how to format line items, trains or one-off activities
Shapes Use for Phase Titles, Maps Titles, Logic Ties, Milestones, etc.

## Work Density
Work Density Table
[35 empty] | Zone | Density
[35 empty] | 1 | 0
[35 empty] | 2 | 0
[35 empty] | 3 | 0
[35 empty] | 4 | 0
[35 empty] | 5 | 0
[35 empty] | 6 | 0
[35 empty] | 7 | 0
[35 empty] | 8 | 0
[35 empty] | 9 | 0
[35 empty] | 10 | 0
[35 empty] | 11 | 0
Creating & populating grid according to our scale
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
|  |  | 0 | 3 | 4 | 4 | 6 | 6 | 6 | 3 | 3 | 3
|  |  | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 7 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 8 | 8 | 8 | 8 | 8
|  |  | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 8 | 8
|  |  | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  |  | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Work density with initial zoning (aggregate scores)
| Work Density Table | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Zone | Density | [6 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 1 | 84 | [6 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 2 | 160 | [6 empty] | 0 | 3 | 4 | 4 | 6 | 6 | 6 | 3 | 3 | 3
| 3 | 159 | [6 empty] | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 4 | 103 | [6 empty] | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 5 | 108 | [6 empty] | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 7 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 6 | 160 | [6 empty] | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 7 | 160 | [6 empty] | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 | 8 | 8 | 8 | 8 | 8
| 8 | 108 | [6 empty] | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 8 | 8 | 8 | 8 | 8
| 9 | 202 | [6 empty] | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 8 | 8
| 10 | 201 | [6 empty] | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 11 | 197 | [6 empty] | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Adjusing areas for a better density leveling
| Work Density Table | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Zone | Density | [5 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 1 | 150 | [5 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| 2 | 152 | [5 empty] | 0 | 3 | 4 | 4 | 6 | 6 | 6 | 3 | 3 | 3
| 3 | 151 | [5 empty] | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 4 | 154 | [5 empty] | 3 | 3 | 6 | 4 | 6 | 6 | 6 | 3 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 5 | 151 | [5 empty] | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 7 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 6 | 152 | [5 empty] | 3 | 3 | 6 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 7 | 150 | [5 empty] | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 | 8 | 8 | 8 | 8 | 8
| 8 | 151 | [5 empty] | 3 | 3 | 4 | 4 | 7 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 8 | 8 | 8 | 8 | 8
| 9 | 156 | [5 empty] | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 8 | 8
| 10 | 156 | [5 empty] | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 11 | 157 | [5 empty] | 2 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Start Here
General process:
1. Study the drawings & understand the level of effort of each area
2. Create your scale and example. Make notes by column square on all drawings
3. Identify any one-off scopes of work that do not represent the average and note them
4. Aggregate your scores
5. Create work densities by column square
6. Adjust if needed
* Example scale for analyising Level of Effort for an interiors phase

## Norm Calculator
|  |  | Macro |  |  | Norm | [5 empty] | General Information
|  |  | Adjusted Takt Wagons | Adjusted Takt Zones | Fixed Takt Time | Fixed Takt Wagons | Adjusted Takt Zones | Takt Time Unrounded | Theoretical Low Limit | Train Length | Adjusted Takt Time | Takt Level | Duration | SSU per Zone | Trade Time Gained | Area per Zone | Realized Flow Potential | Efficiency Parametric | Value Parametric | 28 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200
[21 empty] | 1 | 1: 1; 2: 1; 3: 1; 4: 1; 5: 1; 6: 2; 7: 2; 8: 2; 9: 2; 10: 2; 11: 3; 12: 3; 13: 3; 14: 3; 15: 3; 16: 4; 17: 4; 18: 4; 19: 4; 20: 4; 21: 5; 22: 5; 23: 5; 24: 5; 25: 5; 26: 6; 27: 6; 28: 6; 29: 6; 30: 6; 31: 7; 32: 7; 33: 7; 34: 7; 35: 7; 36: 8; 37: 8; 38: 8; 39: 8; 40: 8; 41: 9; 42: 9; 43: 9; 44: 9; 45: 9; 46: 10; 47: 10; 48: 10; 49: 10; 50: 10; 51: 11; 52: 11; 53: 11; 54: 11; 55: 11; 56: 12; 57: 12; 58: 12; 59: 12; 60: 12; 61: 13; 62: 13; 63: 13; 64: 13; 65: 13; 66: 14; 67: 14; 68: 14; 69: 14; 70: 14; 71: 15; 72: 15; 73: 15; 74: 15; 75: 15
|  |  | 17 | 2 | 5 | 15 | 2 | 10 | 160 | 150 | 10 | Bad | 160 | 12 | 0 | 19770 | 21.25% | 7.5 | 15 |  | 2 | 6: 1; 7: 1; 8: 1; 9: 1; 10: 1; 11: 2; 12: 2; 13: 2; 14: 2; 15: 2; 16: 3; 17: 3; 18: 3; 19: 3; 20: 3; 21: 4; 22: 4; 23: 4; 24: 4; 25: 4; 26: 5; 27: 5; 28: 5; 29: 5; 30: 5; 31: 6; 32: 6; 33: 6; 34: 6; 35: 6; 36: 7; 37: 7; 38: 7; 39: 7; 40: 7; 41: 8; 42: 8; 43: 8; 44: 8; 45: 8; 46: 9; 47: 9; 48: 9; 49: 9; 50: 9; 51: 10; 52: 10; 53: 10; 54: 10; 55: 10; 56: 11; 57: 11; 58: 11; 59: 11; 60: 11; 61: 12; 62: 12; 63: 12; 64: 12; 65: 12; 66: 13; 67: 13; 68: 13; 69: 13; 70: 13; 71: 14; 72: 14; 73: 14; 74: 14; 75: 14; 76: 15; 77: 15; 78: 15; 79: 15; 80: 15
Takt Inputs |  |  | 18 | 3 | 5 | 15 | 3 | 6.6667 | 113.3333 | 105 | 7 | Bad | 119 | 8 | 1 | 13180 | 28.57% | 5 | 7.5 |  | 3 | 11: 1; 12: 1; 13: 1; 14: 1; 15: 1; 16: 2; 17: 2; 18: 2; 19: 2; 20: 2; 21: 3; 22: 3; 23: 3; 24: 3; 25: 3; 26: 4; 27: 4; 28: 4; 29: 4; 30: 4; 31: 5; 32: 5; 33: 5; 34: 5; 35: 5; 36: 6; 37: 6; 38: 6; 39: 6; 40: 6; 41: 7; 42: 7; 43: 7; 44: 7; 45: 7; 46: 8; 47: 8; 48: 8; 49: 8; 50: 8; 51: 9; 52: 9; 53: 9; 54: 9; 55: 9; 56: 10; 57: 10; 58: 10; 59: 10; 60: 10; 61: 11; 62: 11; 63: 11; 64: 11; 65: 11; 66: 12; 67: 12; 68: 12; 69: 12; 70: 12; 71: 13; 72: 13; 73: 13; 74: 13; 75: 13; 76: 14; 77: 14; 78: 14; 79: 14; 80: 14; 81: 15; 82: 15; 83: 15; 84: 15; 85: 15
|  |  | 19 | 4 | 5 | 15 | 4 | 5 | 90 | 75 | 5 | Macro | 90 | 6 | 0 | 9885 | 37.78% | 3.75 | 5 |  | 4 | 16: 1; 17: 1; 18: 1; 19: 1; 20: 1; 21: 2; 22: 2; 23: 2; 24: 2; 25: 2; 26: 3; 27: 3; 28: 3; 29: 3; 30: 3; 31: 4; 32: 4; 33: 4; 34: 4; 35: 4; 36: 5; 37: 5; 38: 5; 39: 5; 40: 5; 41: 6; 42: 6; 43: 6; 44: 6; 45: 6; 46: 7; 47: 7; 48: 7; 49: 7; 50: 7; 51: 8; 52: 8; 53: 8; 54: 8; 55: 8; 56: 9; 57: 9; 58: 9; 59: 9; 60: 9; 61: 10; 62: 10; 63: 10; 64: 10; 65: 10; 66: 11; 67: 11; 68: 11; 69: 11; 70: 11; 71: 12; 72: 12; 73: 12; 74: 12; 75: 12; 76: 13; 77: 13; 78: 13; 79: 13; 80: 13; 81: 14; 82: 14; 83: 14; 84: 14; 85: 14; 86: 15; 87: 15; 88: 15; 89: 15; 90: 15
Takt Wagons |  | 15 | 20 | 5 | 5 | 15 | 5 | 4 | 76 | 60 | 4 | Macro | 76 | 4.8 | 0 | 7908 | 44.74% | 3 | 3.75 |  | 5 | 21: 1; 22: 1; 23: 1; 24: 1; 25: 1; 26: 2; 27: 2; 28: 2; 29: 2; 30: 2; 31: 3; 32: 3; 33: 3; 34: 3; 35: 3; 36: 4; 37: 4; 38: 4; 39: 4; 40: 4; 41: 5; 42: 5; 43: 5; 44: 5; 45: 5; 46: 6; 47: 6; 48: 6; 49: 6; 50: 6; 51: 7; 52: 7; 53: 7; 54: 7; 55: 7; 56: 8; 57: 8; 58: 8; 59: 8; 60: 8; 61: 9; 62: 9; 63: 9; 64: 9; 65: 9; 66: 10; 67: 10; 68: 10; 69: 10; 70: 10; 71: 11; 72: 11; 73: 11; 74: 11; 75: 11; 76: 12; 77: 12; 78: 12; 79: 12; 80: 12; 81: 13; 82: 13; 83: 13; 84: 13; 85: 13; 86: 14; 87: 14; 88: 14; 89: 14; 90: 14; 91: 15; 92: 15; 93: 15; 94: 15; 95: 15
|  |  | 21 | 6 | 5 | 15 | 6 | 3.3333 | 66.6667 | 60 | 4 | Macro | 80 | 4 | 4 | 6590 | 42.5% | 2.5 | 3 |  | 6
Takt Zones |  | 4 | 22 | 7 | 5 | 15 | 7 | 2.8571 | 60 | 45 | 3 | Norm | 63 | 3.4286 | 1 | 5648.5714 | 53.97% | 2.1429 | 2.5 |  | 7
|  |  | 23 | 8 | 5 | 15 | 8 | 2.5 | 55 | 45 | 3 | Norm | 66 | 3 | 4 | 4942.5 | 51.52% | 1.875 | 2.1429 |  | 8
Takt Time |  | 5 | 24 | 9 | 5 | 15 | 9 | 2.2222 | 51.1111 | 45 | 3 | Macro | 69 | 2.6667 | 7 | 4393.3333 | 49.28% | 1.6667 | 1.875 |  | 9
|  |  | 25 | 10 | 5 | 15 | 10 | 2 | 48 | 30 | 2 | Norm | 48 | 2.4 | 0 | 3954 | 70.83% | 1.5 | 1.6667 |  | 10
Duration |  | 90 | 26 | 11 | 5 | 15 | 11 | 1.8182 | 45.4545 | 30 | 2 | Norm | 50 | 2.1818 | 2 | 3594.5455 | 68% | 1.3636 | 1.5 |  | 11
Number of SSU's |  | 24 | 27 | 12 | 5 | 15 | 12 | 1.6667 | 43.3333 | 30 | 2 | Norm | 52 | 2 | 4 | 3295 | 65.38% | 1.25 | 1.3636 |  | 12
|  |  | 28 | 13 | 5 | 15 | 13 | 1.5385 | 41.5385 | 30 | 2 | Norm | 54 | 1.8462 | 6 | 3041.5385 | 62.96% | 1.1538 | 1.25 |  | 13
|  |  | 29 | 14 | 5 | 15 | 14 | 1.4286 | 40 | 30 | 2 | Norm | 56 | 1.7143 | 8 | 2824.2857 | 60.71% | 1.0714 | 1.1538 |  | 14
Area Inputs (m2, sqft) |  |  | 30 | 15 | 5 | 15 | 15 | 1.3333 | 38.6667 | 30 | 2 | Norm | 58 | 1.6 | 10 | 2636 | 58.62% | 1 | 1.0714 |  | 15
|  |  | 31 | 16 | 5 | 15 | 16 | 1.25 | 37.5 | 30 | 2 | Norm | 60 | 1.5 | 12 | 2471.25 | 56.67% | 0.9375 | 1 |  | 16
Area / Zone |  | 9885 | 32 | 17 | 5 | 15 | 17 | 1.1765 | 36.4706 | 30 | 2 | Norm | 62 | 1.4118 | 14 | 2325.8824 | 54.84% | 0.88235 | 0.9375 |  | 17
|  |  | 33 | 18 | 5 | 15 | 18 | 1.1111 | 35.5556 | 30 | 2 | Norm | 64 | 1.3333 | 16 | 2196.6667 | 53.12% | 0.83333 | 0.88235 |  | 18
Min Zone Size |  | 1000 | 34 | 19 | 5 | 15 | 19 | 1.0526 | 34.7368 | 30 | 2 | Norm | 66 | 1.2632 | 18 | 2081.0526 | 51.52% | 0.78947 | 0.83333 |  | 19
|  |  | 35 | 20 | 5 | 15 | 20 | 1 | 34 | 15 | 1 | Norm | 34 | 1.2 | 0 | 1977 | 100% | 0.75 | 0.78947 |  | 20
Max Zone Size |  | 10000 | 36 | 21 | 5 | 15 | 21 | 0.95238 | 33.3333 | 15 | 1 | Norm | 35 | 1.1429 | 1 | 1882.8571 | 97.14% | 0.71429 | 0.75 |  | 21
|  |  | 37 | 22 | 5 | 15 | 22 | 0.90909 | 32.7273 | 15 | 1 | Norm | 36 | 1.0909 | 2 | 1797.2727 | 94.44% | 0.68182 | 0.71429 |  | 22
Total SQFT of Phase |  | 39540 | 38 | 23 | 5 | 15 | 23 | 0.86957 | 32.1739 | 15 | 1 | Norm | 37 | 1.0435 | 3 | 1719.1304 | 91.89% | 0.65217 | 0.68182 |  | 23
|  |  | 39 | 24 | 5 | 15 | 24 | 0.83333 | 31.6667 | 15 | 1 | Norm | 38 | 1 | 4 | 1647.5 | 89.47% | 0.625 | 0.65217 |  | 24
Shortest Durations |  |  | 40 | 25 | 5 | 15 | 25 | 0.8 | 31.2 | 15 | 1 | Norm | 39 | 0.96 | 5 | 1581.6 | 87.18% | 0.6 | 0.625 |  | 25
|  |  | 41 | 26 | 5 | 15 | 26 | 0.76923 | 30.7692 | 15 | 1 | Norm | 40 | 0.92308 | 6 | 1520.7692 | 85% | 0.57692 | 0.6 |  | 26
Best # Zones | Takt Time | Duration | 42 | 27 | 5 | 15 | 27 | 0.74074 | 30.3704 | 15 | 1 | Norm | 41 | 0.88889 | 7 | 1464.4444 | 82.93% | 0.55556 | 0.57692 |  | 27
20 | 1 | 34 | 43 | 28 | 5 | 15 | 28 | 0.71429 | 30 | 15 | 1 | Norm | 42 | 0.85714 | 8 | 1412.1429 | 80.95% | 0.53571 | 0.55556 |  | 28
10 | 2 | 48 | 44 | 29 | 5 | 15 | 29 | 0.68966 | 29.6552 | 15 | 1 | Norm | 43 | 0.82759 | 9 | 1363.4483 | 79.07% | 0.51724 | 0.53571 | x | 29
7 | 3 | 63 | 45 | 30 | 5 | 15 | 30 | 0.66667 | 29.3333 | 15 | 1 | Norm | 44 | 0.8 | 10 | 1318 | 77.27% | 0.5 | 0.51724 |  | 30
5 | 4 | 76 | 46 | 31 | 5 | 15 | 31 | 0.64516 | 29.0323 | 15 | 1 | Norm | 45 | 0.77419 | 11 | 1275.4839 | 75.56% | 0.48387 | 0.5 |  | 31
4 | 5 | 90 | 47 | 32 | 5 | 15 | 32 | 0.625 | 28.75 | 15 | 1 | Norm | 46 | 0.75 | 12 | 1235.625 | 73.91% | 0.46875 | 0.48387 |  | 32
4 | 6 | 108 | 48 | 33 | 5 | 15 | 33 | 0.60606 | 28.4848 | 15 | 1 | Norm | 47 | 0.72727 | 13 | 1198.1818 | 72.34% | 0.45455 | 0.46875 |  | 33
3 | 7 | 119 | 49 | 34 | 5 | 15 | 34 | 0.58824 | 28.2353 | 15 | 1 | Norm | 48 | 0.70588 | 14 | 1162.9412 | 70.83% | 0.44118 | 0.45455 |  | 34
3 | 8 | 136 | 50 | 35 | 5 | 15 | 35 | 0.57143 | 28 | 15 | 1 | Norm | 49 | 0.68571 | 15 | 1129.7143 | 69.39% | 0.42857 | 0.44118 |  | 35
3 | 9 | 153 | 51 | 36 | 5 | 15 | 36 | 0.55556 | 27.7778 | 15 | 1 | Norm | 50 | 0.66667 | 16 | 1098.3333 | 68% | 0.41667 | 0.42857 |  | 36
2 | 10 | 160 | 52 | 37 | 5 | 15 | 37 | 0.54054 | 27.5676 | 15 | 1 | Norm | 51 | 0.64865 | 17 | 1068.6486 | 66.67% | 0.40541 | 0.41667 |  | 37
[21 empty] | 38 | 1: Wagons; 5: 15
[21 empty] | 39 | 1: Zones; 5: 4
[21 empty] | 40 | 1: Takt Time; 5: 5
[22 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200
[21 empty] | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 3 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 4 |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 5 |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 6 | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 7 | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 8 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 9 | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 10 | [9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 11 | [10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 12 | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 13 | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 14 | [13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 15 | [14 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 16 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 17 | [16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 18 | [17 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 19 | [18 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 20 | [19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 21 | [20 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 22 | [21 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 23 | [22 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 24 | [23 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 25 | [24 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 26 | [25 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 27 | [26 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 28 | [27 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[21 empty] | 29 | [28 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
30
31
32
33
34
35
36
37
[21 empty] | 38 | Wagons |  |  |  | 15
[21 empty] | 39 | Zones |  |  |  | 29
[21 empty] | 40 | Takt Time |  |  |  | 1
Optimize the Takt Phase
Overflow Warning
Overflow Warning
Overflow Warning
Overflow Warning
Overflow Warning

## Buyout & Procurement Log
[34 empty] | Today: | 2025-07-11
[34 empty] | Week of the year: | 28
Spec Section | Takt Zone | Scope of Work | Selected Subcontractor | RFP To Subcontractor | RFI & PREQ. Prep WKS | RFI & PREQ. Due | RFI Due To Sub Visit Start WKS | Start Trade Partner Site Visit | Trade Visit Start To Bids due WKS | Bids Due | Bid Review WKS | Client Presentation & Sub Selection | Approvals & NTP WKS | Start Contracting with Sub | Contracting Process Time (WKS) | Drop Dead Subcontract Execution | Subcontract Executed | Submittal Prep WKS | Receive Submittal | Actual Approved Submittal | Submittal Review WKS | Sent To Design Team | Design Approved | Design Team Approval Wks. | Release Date (Order Materials By) | Confirmed Release Date | Submittal Over/Under Days | Lead Time WKS | Ship Date | Delivery Weeks | Buffer Duration WEEKS | Actual Date on Site | Required On Job (Get Superintendent Input!) | Material Over/Under DAYS | Notes | Last Date of Contact
Toggle Light Switches | 2 | Electrical | Electrical Services | 2023-07-27 | 1 | 2023-08-03 | 1 | 2023-08-10 | 1 | 2023-08-17 | 1 | 2023-08-24 | 1 | 2023-08-31 | 1 | 2023-09-07 |  | 1 | 2023-09-14 |  | 1 | 2023-09-21 |  | 1 | 2023-09-28 |  |  | 5 | 2023-11-02 | 1 | 1 |  | 2023-11-16
Duplex Receptacles | 2 | Electrical | Electrical Services | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 |  | 0 | 2024-10-12 |  | 0 | 2024-10-12 |  | 0 | 2024-10-12 |  |  | 3 | 2024-11-02 | 2 | 0 |  | 2024-11-16
Recessed lighting | 2 | Electrical | Electrical Services | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 |  | 0 | 2024-09-14 |  | 0 | 2024-09-14 |  | 0 | 2024-09-14 |  |  | 5 | 2024-10-19 | 2 | 2 |  | 2024-11-16
Cabinets | 2 | Casework | Cabintes & More LLC | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 |  | 0 | 2024-08-01 |  | 0 | 2024-08-01 |  | 0 | 2024-08-01 |  |  | 14 | 2024-11-07 | 3 | 0 |  | 2024-11-28
Drawers | 2 | Casework | Cabintes & More LLC | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 2023-12-30 | 0 | 2024-10-10 |  | 0 | 2024-10-10 |  | 0 | 2024-10-10 |  | -285 | 4 | 2024-11-07 | 2 | 1 |  | 2024-11-28
Bookshelves | 2 | Casework | Cabintes & More LLC | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 |  | 0 | 2024-10-03 |  | 0 | 2024-10-03 |  | 0 | 2024-10-03 |  |  | 7 | 2024-11-21 | 1 | 0 |  | 2024-11-28
Windows | 2 | Millwork | Doors & Windows Inc | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 |  | 0 | 2024-08-30 |  | 0 | 2024-08-30 |  | 0 | 2024-08-30 |  |  | 8 | 2024-10-25 | 5 | 1 |  | 2024-12-06
Doors | 2 | Millwork | Doors & Windows Inc | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 |  | 0 | 2024-10-11 |  | 0 | 2024-10-11 |  | 0 | 2024-10-11 |  |  | 4 | 2024-11-08 | 3 | 1 |  | 2024-12-06
Light Fixtures | 2 | Electrical | Electrical Services | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 |  | 0 | 2024-06-22 |  | 0 | 2024-06-22 |  | 0 | 2024-06-22 |  |  | 20 | 2024-11-09 | 1 | 0 |  | 2024-11-16
Electric Sockets | 2 | Electrical | Electrical Services | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  |  | 3 | 2024-10-26 | 2 | 1 |  | 2024-11-16
Security Alarm System | 2 | Electrical | Electrical Services | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 |  | 0 | 2024-10-19 |  | 0 | 2024-10-19 |  | 0 | 2024-10-19 |  |  | 2 | 2024-11-02 | 2 | 0 |  | 2024-11-16
Fire Alarm | 2 | Electrical | Electrical Services | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  |  | 2 | 2024-10-19 | 2 | 2 |  | 2024-11-16
Kitchens | 2 | Casework | Kitchens Inc | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 2023-12-30 | 0 | 2024-08-31 |  | 0 | 2024-08-31 |  | 0 | 2024-08-31 |  | -245 | 10 | 2024-11-09 | 2 | 1 |  | 2024-11-30
|  |  |  | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 |  | 29 | 2025-09-12 |  | 2 | 2025-09-26 |  | 10 | 2025-12-05 |  |  | 0 | 2025-12-05 | 1 | 0 |  | 2025-12-12
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
**ITEMS IN RED ARE IN TROUBLE** | [34 empty] | LAST DATE REVIEWED W/ SUPER:
Formulas:
RFP To Subcontractor = IF([RFI & PREQ. Due]="","",[RFI & PREQ. Due]-(7*[RFI & PREQ. Prep WKS]))
RFI & PREQ. Due = IF([Start Trade Partner Site Visit]="","",[Start Trade Partner Site Visit]-(7*[RFI Due To Sub Visit Start WKS]))
Start Trade Partner Site Visit = IF([Bids Due]="","",[Bids Due]-(7*[Trade Visit Start To Bids due WKS]))
Bids Due = IF([Client Presentation & Sub Selection]="","",[Client Presentation & Sub Selection]-(7*[Bid Review WKS]))
Client Presentation & Sub Selection = IF([Start Contracting with Sub]="","",[Start Contracting with Sub]-(7*[Approvals & NTP WKS]))
Start Contracting with Sub = IF([Drop Dead Subcontract Execution]="","",[Drop Dead Subcontract Execution]-(7*[Contracting Process Time (WKS)]))
Drop Dead Subcontract Execution = IF([Receive Submittal]="","",[Receive Submittal]-(7*[Submittal Prep WKS]))
Receive Submittal = IF([Sent To Design Team]="","",[Sent To Design Team]-([Submittal Review WKS]*7))
Sent To Design Team = IF([Release Date (Order Materials By)]="","",[Release Date (Order Materials By)]-([Design Team Approval Wks.]*7))
Release Date (Order Materials By) = IF([Ship Date]="","",[Ship Date]-(7*[Lead Time WKS]))
Ship Date = IF(AJ6="","",AJ6-(7*[Delivery Weeks])-(7*[Buffer Duration WEEKS]))
1
2
3
7
1
3
2
1
2
3
7
How to use Procurement Log:
1. Fill in the Spec Section, Scope of Work, Takt Zone and Trade Partner.
2. Start with the "Required on Job" date (you can obtain this from the norm-level takt plan).
3. Fill in the estimated delivery weeks and if considered, the buffer weeks.
4. Ship Dates will be updated automatically.
5. Add the Lead Time Weeks. (Required Submittal Approval will update automatically).
6. Fill in addtional work weeks such as Submittal Prep & Review WKS and "Design Team Approval WKS.
7. When the actual Released TP and Approved Submittal date is obtained, it is necesasay to fill it in manually.
NOTES: Only the "Required on Job" date is necessary to fill in, the other dates will update according the added information. Comment section can be used for special considerations or additional conditions for the log entry.
Information Needed
Automatically
BUYOUT
PROCUREMENT
Date is 1 to 14 days ahead
Date is 15+ days ahead
Date is today or past
Conditional Formatting Legend

## Full Norm - Example
|  |  | 2022 | [19 empty] | 2022 | [19 empty] | 2022 | [19 empty] | 2022 | [24 empty] | 2022 | [19 empty] | 2022 | [19 empty] | 2022 | [24 empty] | 2022 | [19 empty] | 2022 | [24 empty] | 2022 | [19 empty] | 2022 | [19 empty] | 2023 | [21 empty] | 2023 | [19 empty] | 2023 | [22 empty] | 2023 | [19 empty] | 2023 | [22 empty] | 2023 | [21 empty] | 2023 | [20 empty] | 2023 | [22 empty] | 2023 | [20 empty] | 2023 | [21 empty] | 2023 | [21 empty] | 2023
|  |  | February | [19 empty] | March | [19 empty] | April | [19 empty] | May | [24 empty] | June | [19 empty] | July | [19 empty] | August | [24 empty] | September | [19 empty] | October | [24 empty] | November | [19 empty] | December | [19 empty] | January | [21 empty] | February | [19 empty] | March | [22 empty] | April | [19 empty] | May | [22 empty] | June | [21 empty] | July | [20 empty] | August | [22 empty] | September | [20 empty] | October | [21 empty] | November | [21 empty] | December
|  |  | 2022-02-07 |  |  |  |  | 2022-02-14 |  |  |  |  | 2022-02-21 |  |  |  |  | 2022-02-28 |  |  |  |  | 2022-03-07 |  |  |  |  | 2022-03-14 |  |  |  |  | 2022-03-21 |  |  |  |  | 2022-03-28 |  |  |  |  | 2022-04-04 |  |  |  |  | 2022-04-11 |  |  |  |  | 2022-04-18 |  |  |  |  | 2022-04-25 |  |  |  |  | 2022-05-02 |  |  |  |  | 2022-05-09 |  |  |  |  | 2022-05-16 |  |  |  |  | 2022-05-23 |  |  |  |  | 2022-05-30 |  |  |  |  | 2022-06-06 |  |  |  |  | 2022-06-13 |  |  |  |  | 2022-06-20 |  |  |  |  | 2022-06-27 |  |  |  |  | 2022-07-04 |  |  |  |  | 2022-07-11 |  |  |  |  | 2022-07-18 |  |  |  |  | 2022-07-25 |  |  |  |  | 2022-08-01 |  |  |  |  | 2022-08-08 |  |  |  |  | 2022-08-15 |  |  |  |  | 2022-08-22 |  |  |  |  | 2022-08-29 |  |  |  |  | 2022-09-05 |  |  |  |  | 2022-09-12 |  |  |  |  | 2022-09-19 |  |  |  |  | 2022-09-26 |  |  |  |  | 2022-10-03 |  |  |  |  | 2022-10-10 |  |  |  |  | 2022-10-17 |  |  |  |  | 2022-10-24 |  |  |  |  | 2022-10-31 |  |  |  |  | 2022-11-07 |  |  |  |  | 2022-11-14 |  |  |  |  | 2022-11-21 |  |  |  |  | 2022-11-28 |  |  |  |  | 2022-12-05 |  |  |  |  | 2022-12-12 |  |  |  |  | 2022-12-19 |  |  |  |  | 2022-12-26 |  |  |  |  | 2023-01-02 |  |  |  |  | 2023-01-09 |  |  |  |  | 2023-01-16 |  |  |  |  | 2023-01-23 |  |  |  |  | 2023-01-30 |  |  |  |  | 2023-02-06 |  |  |  |  | 2023-02-13 |  |  |  |  | 2023-02-20 |  |  |  |  | 2023-02-27 |  |  |  |  | 2023-03-06 |  |  |  |  | 2023-03-13 |  |  |  |  | 2023-03-20 |  |  |  |  | 2023-03-27 |  |  |  |  | 2023-04-03 |  |  |  |  | 2023-04-10 |  |  |  |  | 2023-04-17 |  |  |  |  | 2023-04-24 |  |  |  |  | 2023-05-01 |  |  |  |  | 2023-05-08 |  |  |  |  | 2023-05-15 |  |  |  |  | 2023-05-22 |  |  |  |  | 2023-05-29 |  |  |  |  | 2023-06-05 |  |  |  |  | 2023-06-12 |  |  |  |  | 2023-06-19 |  |  |  |  | 2023-06-26 |  |  |  |  | 2023-07-03 |  |  |  |  | 2023-07-10 |  |  |  |  | 2023-07-17 |  |  |  |  | 2023-07-24 |  |  |  |  | 2023-07-31 |  |  |  |  | 2023-08-07 |  |  |  |  | 2023-08-14 |  |  |  |  | 2023-08-21 |  |  |  |  | 2023-08-28 |  |  |  |  | 2023-09-04 |  |  |  |  | 2023-09-11 |  |  |  |  | 2023-09-18 |  |  |  |  | 2023-09-25 |  |  |  |  | 2023-10-02 |  |  |  |  | 2023-10-09 |  |  |  |  | 2023-10-16 |  |  |  |  | 2023-10-23 |  |  |  |  | 2023-10-30 |  |  |  |  | 2023-11-06 |  |  |  |  | 2023-11-13 |  |  |  |  | 2023-11-20 |  |  |  |  | 2023-11-27 |  |  |  |  | 2023-12-04 |  |  |  |  | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29
 | time axis 2022-02-07 to 2023-12-29
 | time axis 2022-02-07 to 2023-12-29
|  | PRE-CON MEETINGS | 2023-02-03: North Exterioirs EIFS
[252 empty] | Level 2 Zone E&F Framing | [9 empty] | Level 3 Fire Sprinkler |  |  |  |  | Level 3 OH MEP
|  | MILESTONES | 2023-04-19: 🔶; 2023-04-20: Air On
[13 empty] | 🔶 | Notice to Proceed | [63 empty] | 🔷 | Sitework Complete | [60 empty] | 🔷 | Foundation Complete | [63 empty] | 🔷 | Structure complete | [86 empty] | 🔶 | Power On | [9 empty] | 🔷 | Exterior Complete | [70 empty] | 🔷 | Interior Complete | [30 empty] | 🔶 | Substantial Completion | [18 empty] | 🔶 | Final Completion + Financial Completion
|  | PROCUREMENT | 2022-08-22: Electrical Gear; 2023-01-30: SES Fit-out & Energize
HVAC Equipment
Windows
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
BEGINNING SITEWORK WORK |  |  | 2022-02-21: MOBILIZATION; 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
1H | Excavation/Grading |  | 2022-02-28: 1H; 2022-03-01: 1H; 2022-03-02: 1H; 2022-03-03: 1H; 2022-03-04: 1H; 2022-03-07: 1H; 2022-03-08: 1H; 2022-03-09: 1H; 2022-03-10: 1H; 2022-03-11: 1H; 2022-03-14: 1H; 2022-03-15: 1H; 2022-03-16: 1H; 2022-03-17: 1H; 2022-03-18: 1H; 2022-03-21: 1I; 2022-03-22: 1I; 2022-03-23: 1I; 2022-03-24: 1I; 2022-03-25: 1I; 2022-03-28: 1I; 2022-03-29: 1I; 2022-03-30: 1I; 2022-03-31: 1I; 2022-04-01: 1I; 2022-04-04: 1I; 2022-04-05: 1I; 2022-04-06: 1I; 2022-04-07: 1I; 2022-04-08: 1I; 2022-04-11: 1I; 2022-04-12: 1I; 2022-04-13: 1I; 2022-04-14: 1I; 2022-04-15: 1I; 2022-04-18: 1J; 2022-04-19: 1J; 2022-04-20: 1J; 2022-04-21: 1J; 2022-04-22: 1J; 2022-04-25: 1J; 2022-04-26: 1J; 2022-04-27: 1J; 2022-04-28: 1J; 2022-04-29: 1J; 2022-05-02: 1J; 2022-05-03: 1J; 2022-05-04: 1J; 2022-05-05: 1J; 2022-05-06: 1J; 2022-05-09: 1J; 2022-05-10: 1J; 2022-05-11: 1J; 2022-05-12: 1J; 2022-05-13: 1J; 2022-05-16: 1K; 2022-05-17: 1K; 2022-05-18: 1K; 2022-05-19: 1K; 2022-05-20: 1K; 2022-05-23: B; 2022-05-24: B; 2022-05-25: B; 2022-05-26: B; 2022-05-27: B; 2022-05-30: B; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
1I | Install Storm/Sanitary/Water/Dry U.G. Utilities | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
1J | Parking Area Base Stone | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
1K | Final Grading | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [33 empty] | Shaft Prep | [29 empty] | Elevator Cabs | [29 empty] | Certification | [14 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H |  |  |  | Comeback Areas for Elev | [21 empty] | H | [44 empty] | H
[82 empty] | ZONE A | H | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F3 | F3 | F3 | F3 | H | F3 | F3 | F3 | F3 | F3 | F3 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | B | B | B | B | B | B | B | B | [17 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
FOUNDATION LEGEND |  |  | 2022-05-30: H; 2022-06-13: ZONE B; 2022-06-14: F1; 2022-06-15: F1; 2022-06-16: F1; 2022-06-17: F1; 2022-06-20: F1; 2022-06-21: F1; 2022-06-22: F1; 2022-06-23: F1; 2022-06-24: F1; 2022-06-27: F1; 2022-06-28: F2; 2022-06-29: F2; 2022-06-30: F2; 2022-07-01: F2; 2022-07-04: H; 2022-07-05: F2; 2022-07-06: F2; 2022-07-07: F2; 2022-07-08: F2; 2022-07-11: F2; 2022-07-12: F2; 2022-07-13: F3; 2022-07-14: F3; 2022-07-15: F3; 2022-07-18: F3; 2022-07-19: F3; 2022-07-20: F3; 2022-07-21: F3; 2022-07-22: F3; 2022-07-25: F3; 2022-07-26: F3; 2022-07-27: F4; 2022-07-28: F4; 2022-07-29: F4; 2022-08-01: F4; 2022-08-02: F4; 2022-08-03: F4; 2022-08-04: F4; 2022-08-05: F4; 2022-08-08: F4; 2022-08-09: F4; 2022-08-10: F4; 2022-08-11: F4; 2022-08-12: F4; 2022-08-15: F4; 2022-08-16: F4; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-05: Erect Stair 1; 2022-12-26: H; 2022-12-27: H; 2023-01-04: Erect Stair 2; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
F1 | Excavate & Pour Footings |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-04: Pour 1; 2023-02-01: Pour 2; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
F2 | Columns & Walls | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
F3 | UG MEP | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
F4 | SOG | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
B | Buffer | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
[83 empty] | H | [24 empty] | H | [28 empty] | LEVEL 1A | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | H | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [31 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [31 empty] | LEVEL 1B | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | H | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [28 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [34 empty] | LEVEL 2A | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | H | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [25 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [37 empty] | LEVEL 2B | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S1 | H | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [22 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [40 empty] | LEVEL 3A | S1 | S1 | S1 | S1 | S1 | H | S1 | S1 | S1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S2 | S3 | S3 | S3 | S3 | S3 | S3 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | S4 | [19 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
STRUCTURE LEGEND |  |  | 2022-05-30: H; 2022-07-04: H; 2022-09-02: LEVEL 3B; 2022-09-05: S1; 2022-09-06: S1; 2022-09-07: H; 2022-09-08: S1; 2022-09-09: S1; 2022-09-12: S1; 2022-09-13: S1; 2022-09-14: S1; 2022-09-15: S1; 2022-09-16: S1; 2022-09-19: S1; 2022-09-20: S1; 2022-09-21: S1; 2022-09-22: S2; 2022-09-23: S2; 2022-09-26: S2; 2022-09-27: S2; 2022-09-28: S2; 2022-09-29: S2; 2022-09-30: S2; 2022-10-03: S2; 2022-10-04: S2; 2022-10-05: S2; 2022-10-06: S2; 2022-10-07: S2; 2022-10-10: S3; 2022-10-11: S3; 2022-10-12: S3; 2022-10-13: S3; 2022-10-14: S3; 2022-10-17: S3; 2022-10-18: S4; 2022-10-19: S4; 2022-10-20: S4; 2022-10-21: S4; 2022-10-24: S4; 2022-10-25: S4; 2022-10-26: S4; 2022-10-27: S4; 2022-10-28: S4; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
S1 | Deck Formwork |  | 2022-05-30: H; 2022-07-04: H; 2022-09-08: LEVEL 4A; 2022-09-09: S1; 2022-09-12: S1; 2022-09-13: S1; 2022-09-14: S1; 2022-09-15: S1; 2022-09-16: S1; 2022-09-19: S1; 2022-09-20: S1; 2022-09-21: S1; 2022-09-22: S1; 2022-09-23: S1; 2022-09-26: S1; 2022-09-27: S2; 2022-09-28: S2; 2022-09-29: S2; 2022-09-30: S2; 2022-10-03: S2; 2022-10-04: S2; 2022-10-05: S2; 2022-10-06: S2; 2022-10-07: S2; 2022-10-10: S2; 2022-10-11: S2; 2022-10-12: S2; 2022-10-13: S3; 2022-10-14: S3; 2022-10-17: S3; 2022-10-18: S3; 2022-10-19: S3; 2022-10-20: S3; 2022-10-21: S4; 2022-10-24: S4; 2022-10-25: S4; 2022-10-26: S4; 2022-10-27: S4; 2022-10-28: S4; 2022-10-31: S4; 2022-11-01: S4; 2022-11-02: S4; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
S2 | Deck MEP & Reinforcing |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-09-13: LEVEL 4B; 2022-09-14: S1; 2022-09-15: S1; 2022-09-16: S1; 2022-09-19: S1; 2022-09-20: S1; 2022-09-21: S1; 2022-09-22: S1; 2022-09-23: S1; 2022-09-26: S1; 2022-09-27: S1; 2022-09-28: S1; 2022-09-29: S1; 2022-09-30: S2; 2022-10-03: S2; 2022-10-04: S2; 2022-10-05: S2; 2022-10-06: S2; 2022-10-07: S2; 2022-10-10: S2; 2022-10-11: S2; 2022-10-12: S2; 2022-10-13: S2; 2022-10-14: S2; 2022-10-17: S2; 2022-10-18: S3; 2022-10-19: S3; 2022-10-20: S3; 2022-10-21: S3; 2022-10-24: S3; 2022-10-25: S3; 2022-10-26: S4; 2022-10-27: S4; 2022-10-28: S4; 2022-10-31: S4; 2022-11-01: S4; 2022-11-02: S4; 2022-11-03: S4; 2022-11-04: S4; 2022-11-07: S4; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
S3 | Deck Inspections & Place |  | 2022-02-18: Notice to Proceed; 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-09-16: LEVEL 5A; 2022-09-19: S1; 2022-09-20: S1; 2022-09-21: S1; 2022-09-22: S1; 2022-09-23: S1; 2022-09-26: S1; 2022-09-27: S1; 2022-09-28: S1; 2022-09-29: S1; 2022-09-30: S1; 2022-10-03: S1; 2022-10-04: S1; 2022-10-05: S2; 2022-10-06: S2; 2022-10-07: S2; 2022-10-10: S2; 2022-10-11: S2; 2022-10-12: S2; 2022-10-13: S2; 2022-10-14: S2; 2022-10-17: S2; 2022-10-18: S2; 2022-10-19: S2; 2022-10-20: S2; 2022-10-21: S3; 2022-10-24: S3; 2022-10-25: S3; 2022-10-26: S3; 2022-10-27: S3; 2022-10-28: S3; 2022-10-31: S4; 2022-11-01: S4; 2022-11-02: S4; 2022-11-03: S4; 2022-11-04: S4; 2022-11-07: S4; 2022-11-08: S4; 2022-11-09: S4; 2022-11-10: S4; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-05-29: H; 2023-07-04: H; 2023-08-25: Substantial Completion; 2023-09-05: H; 2023-09-22: Final Completion + Financial Completion
S4 | Columns & Walls |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-09-21: LEVEL 5B; 2022-09-22: S1; 2022-09-23: S1; 2022-09-26: S1; 2022-09-27: S1; 2022-09-28: S1; 2022-09-29: S1; 2022-09-30: S1; 2022-10-03: S1; 2022-10-04: S1; 2022-10-05: S1; 2022-10-06: S1; 2022-10-07: S1; 2022-10-10: S2; 2022-10-11: S2; 2022-10-12: S2; 2022-10-13: S2; 2022-10-14: S2; 2022-10-17: S2; 2022-10-18: S2; 2022-10-19: S2; 2022-10-20: S2; 2022-10-21: S2; 2022-10-24: S2; 2022-10-25: S2; 2022-10-26: S3; 2022-10-27: S3; 2022-10-28: S3; 2022-10-31: S3; 2022-11-01: S3; 2022-11-02: S3; 2022-11-03: S4; 2022-11-04: S4; 2022-11-07: S4; 2022-11-08: S4; 2022-11-09: S4; 2022-11-10: S4; 2022-11-11: S4; 2022-11-14: S4; 2022-11-15: S4; 2022-11-16: B; 2022-11-17: B; 2022-11-18: B; 2022-11-21: B; 2022-11-22: B; 2022-11-23: B; 2022-11-24: B; 2022-11-25: B; 2022-11-28: B; 2022-11-29: B; 2022-11-30: B; 2022-12-01: B; 2022-12-02: B; 2022-12-05: B; 2022-12-06: B; 2022-12-07: B; 2022-12-08: B; 2022-12-09: B; 2022-12-12: B; 2022-12-13: B; 2022-12-14: B; 2022-12-15: B; 2022-12-16: B; 2022-12-19: B; 2022-12-20: B; 2022-12-21: B; 2022-12-22: B; 2022-12-26: H; 2022-12-27: H; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [18 empty] | ZONE 1A | 1 | H | H | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [55 empty] | H | [25 empty] | H | [44 empty] | H
INTERIOR LEGEND |  |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-29: ZONE 1B; 2022-12-30: 1; 2023-01-02: 1; 2023-01-03: 1; 2023-01-04: 2; 2023-01-05: 2; 2023-01-06: 2; 2023-01-09: 3; 2023-01-10: 3; 2023-01-11: 3; 2023-01-12: 4; 2023-01-13: 4; 2023-01-16: 4; 2023-01-17: 5; 2023-01-18: 5; 2023-01-19: 5; 2023-01-20: 6; 2023-01-23: 6; 2023-01-24: 6; 2023-01-25: B; 2023-01-26: B; 2023-01-27: B; 2023-01-30: 7; 2023-01-31: 7; 2023-02-01: 7; 2023-02-02: 8; 2023-02-03: 8; 2023-02-06: 8; 2023-02-07: B; 2023-02-08: B; 2023-02-09: B; 2023-02-10: 9; 2023-02-13: 9; 2023-02-14: 9; 2023-02-15: 10; 2023-02-16: 10; 2023-02-17: 10; 2023-02-20: 11; 2023-02-21: 11; 2023-02-22: 11; 2023-02-23: 12; 2023-02-24: 12; 2023-02-27: 12; 2023-02-28: 13; 2023-03-01: 13; 2023-03-02: 13; 2023-03-03: B; 2023-03-06: B; 2023-03-07: B; 2023-03-08: 14; 2023-03-09: 14; 2023-03-10: 14; 2023-03-13: 15; 2023-03-14: 15; 2023-03-15: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
1 | Remove Reshores, Floor Prep & Wall Layout |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-03: ZONE 1C; 2023-01-04: 1; 2023-01-05: 1; 2023-01-06: 1; 2023-01-09: 2; 2023-01-10: 2; 2023-01-11: 2; 2023-01-12: 3; 2023-01-13: 3; 2023-01-16: 3; 2023-01-17: 4; 2023-01-18: 4; 2023-01-19: 4; 2023-01-20: 5; 2023-01-23: 5; 2023-01-24: 5; 2023-01-25: 6; 2023-01-26: 6; 2023-01-27: 6; 2023-01-30: B; 2023-01-31: B; 2023-02-01: B; 2023-02-02: 7; 2023-02-03: 7; 2023-02-06: 7; 2023-02-07: 8; 2023-02-08: 8; 2023-02-09: 8; 2023-02-10: B; 2023-02-13: B; 2023-02-14: B; 2023-02-15: 9; 2023-02-16: 9; 2023-02-17: 9; 2023-02-20: 10; 2023-02-21: 10; 2023-02-22: 10; 2023-02-23: 11; 2023-02-24: 11; 2023-02-27: 11; 2023-02-28: 12; 2023-03-01: 12; 2023-03-02: 12; 2023-03-03: 13; 2023-03-06: 13; 2023-03-07: 13; 2023-03-08: B; 2023-03-09: B; 2023-03-10: B; 2023-03-13: 14; 2023-03-14: 14; 2023-03-15: 14; 2023-03-16: 15; 2023-03-17: 15; 2023-03-20: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
2 | Fire Sprinkler & Install Walls | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
3 | OH Mechanical Duct | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
4 | OH Mech Equip, Piping, Branch Lines & Plumbing |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-06: ZONE 2A; 2023-01-09: 1; 2023-01-10: 1; 2023-01-11: 1; 2023-01-12: 2; 2023-01-13: 2; 2023-01-16: 2; 2023-01-17: 3; 2023-01-18: 3; 2023-01-19: 3; 2023-01-20: 4; 2023-01-23: 4; 2023-01-24: 4; 2023-01-25: 5; 2023-01-26: 5; 2023-01-27: 5; 2023-01-30: 6; 2023-01-31: 6; 2023-02-01: 6; 2023-02-02: B; 2023-02-03: B; 2023-02-06: B; 2023-02-07: 7; 2023-02-08: 7; 2023-02-09: 7; 2023-02-10: 8; 2023-02-13: 8; 2023-02-14: 8; 2023-02-15: B; 2023-02-16: B; 2023-02-17: B; 2023-02-20: 9; 2023-02-21: 9; 2023-02-22: 9; 2023-02-23: 10; 2023-02-24: 10; 2023-02-27: 10; 2023-02-28: 11; 2023-03-01: 11; 2023-03-02: 11; 2023-03-03: 12; 2023-03-06: 12; 2023-03-07: 12; 2023-03-08: 13; 2023-03-09: 13; 2023-03-10: 13; 2023-03-13: B; 2023-03-14: B; 2023-03-15: B; 2023-03-16: 14; 2023-03-17: 14; 2023-03-20: 14; 2023-03-21: 15; 2023-03-22: 15; 2023-03-23: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
5 | OH Electrical & Frame Walls |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-11: ZONE 2B; 2023-01-12: 1; 2023-01-13: 1; 2023-01-16: 1; 2023-01-17: 2; 2023-01-18: 2; 2023-01-19: 2; 2023-01-20: 3; 2023-01-23: 3; 2023-01-24: 3; 2023-01-25: 4; 2023-01-26: 4; 2023-01-27: 4; 2023-01-30: 5; 2023-01-31: 5; 2023-02-01: 5; 2023-02-02: 6; 2023-02-03: 6; 2023-02-06: 6; 2023-02-07: B; 2023-02-08: B; 2023-02-09: B; 2023-02-10: 7; 2023-02-13: 7; 2023-02-14: 7; 2023-02-15: 8; 2023-02-16: 8; 2023-02-17: 8; 2023-02-20: B; 2023-02-21: B; 2023-02-22: B; 2023-02-23: 9; 2023-02-24: 9; 2023-02-27: 9; 2023-02-28: 10; 2023-03-01: 10; 2023-03-02: 10; 2023-03-03: 11; 2023-03-06: 11; 2023-03-07: 11; 2023-03-08: 12; 2023-03-09: 12; 2023-03-10: 12; 2023-03-13: 13; 2023-03-14: 13; 2023-03-15: 13; 2023-03-16: B; 2023-03-17: B; 2023-03-20: B; 2023-03-21: 14; 2023-03-22: 14; 2023-03-23: 14; 2023-03-24: 15; 2023-03-27: 15; 2023-03-28: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
6 | Frame Walls, Install In-wall Electrical & Plumbing |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-16: ZONE 2C; 2023-01-17: 1; 2023-01-18: 1; 2023-01-19: 1; 2023-01-20: 2; 2023-01-23: 2; 2023-01-24: 2; 2023-01-25: 3; 2023-01-26: 3; 2023-01-27: 3; 2023-01-30: 4; 2023-01-31: 4; 2023-02-01: 4; 2023-02-02: 5; 2023-02-03: 5; 2023-02-06: 5; 2023-02-07: 6; 2023-02-08: 6; 2023-02-09: 6; 2023-02-10: B; 2023-02-13: B; 2023-02-14: B; 2023-02-15: 7; 2023-02-16: 7; 2023-02-17: 7; 2023-02-20: 8; 2023-02-21: 8; 2023-02-22: 8; 2023-02-23: B; 2023-02-24: B; 2023-02-27: B; 2023-02-28: 9; 2023-03-01: 9; 2023-03-02: 9; 2023-03-03: 10; 2023-03-06: 10; 2023-03-07: 10; 2023-03-08: 11; 2023-03-09: 11; 2023-03-10: 11; 2023-03-13: 12; 2023-03-14: 12; 2023-03-15: 12; 2023-03-16: 13; 2023-03-17: 13; 2023-03-20: 13; 2023-03-21: B; 2023-03-22: B; 2023-03-23: B; 2023-03-24: 14; 2023-03-27: 14; 2023-03-28: 14; 2023-03-29: 15; 2023-03-30: 15; 2023-03-31: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
7 | In-wall Process Piping, 1st Drywall, Insulation & Insp |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-19: ZONE 2D; 2023-01-20: 1; 2023-01-23: 1; 2023-01-24: 1; 2023-01-25: 2; 2023-01-26: 2; 2023-01-27: 2; 2023-01-30: 3; 2023-01-31: 3; 2023-02-01: 3; 2023-02-02: 4; 2023-02-03: 4; 2023-02-06: 4; 2023-02-07: 5; 2023-02-08: 5; 2023-02-09: 5; 2023-02-10: 6; 2023-02-13: 6; 2023-02-14: 6; 2023-02-15: B; 2023-02-16: B; 2023-02-17: B; 2023-02-20: 7; 2023-02-21: 7; 2023-02-22: 7; 2023-02-23: 8; 2023-02-24: 8; 2023-02-27: 8; 2023-02-28: B; 2023-03-01: B; 2023-03-02: B; 2023-03-03: 9; 2023-03-06: 9; 2023-03-07: 9; 2023-03-08: 10; 2023-03-09: 10; 2023-03-10: 10; 2023-03-13: 11; 2023-03-14: 11; 2023-03-15: 11; 2023-03-16: 12; 2023-03-17: 12; 2023-03-20: 12; 2023-03-21: 13; 2023-03-22: 13; 2023-03-23: 13; 2023-03-24: B; 2023-03-27: B; 2023-03-28: B; 2023-03-29: 14; 2023-03-30: 14; 2023-03-31: 14; 2023-04-03: 15; 2023-04-04: 15; 2023-04-05: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
8 | Finish Walls & Painting |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-24: ZONE 2E; 2023-01-25: 1; 2023-01-26: 1; 2023-01-27: 1; 2023-01-30: 2; 2023-01-31: 2; 2023-02-01: 2; 2023-02-02: 3; 2023-02-03: 3; 2023-02-06: 3; 2023-02-07: 4; 2023-02-08: 4; 2023-02-09: 4; 2023-02-10: 5; 2023-02-13: 5; 2023-02-14: 5; 2023-02-15: 6; 2023-02-16: 6; 2023-02-17: 6; 2023-02-20: B; 2023-02-21: B; 2023-02-22: B; 2023-02-23: 7; 2023-02-24: 7; 2023-02-27: 7; 2023-02-28: 8; 2023-03-01: 8; 2023-03-02: 8; 2023-03-03: B; 2023-03-06: B; 2023-03-07: B; 2023-03-08: 9; 2023-03-09: 9; 2023-03-10: 9; 2023-03-13: 10; 2023-03-14: 10; 2023-03-15: 10; 2023-03-16: 11; 2023-03-17: 11; 2023-03-20: 11; 2023-03-21: 12; 2023-03-22: 12; 2023-03-23: 12; 2023-03-24: 13; 2023-03-27: 13; 2023-03-28: 13; 2023-03-29: B; 2023-03-30: B; 2023-03-31: B; 2023-04-03: 14; 2023-04-04: 14; 2023-04-05: 14; 2023-04-06: 15; 2023-04-07: 15; 2023-04-10: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
9 | Painting & Install Ceiling Grid |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-27: ZONE 2F; 2023-01-30: 1; 2023-01-31: 1; 2023-02-01: 1; 2023-02-02: 2; 2023-02-03: 2; 2023-02-06: 2; 2023-02-07: 3; 2023-02-08: 3; 2023-02-09: 3; 2023-02-10: 4; 2023-02-13: 4; 2023-02-14: 4; 2023-02-15: 5; 2023-02-16: 5; 2023-02-17: 5; 2023-02-20: 6; 2023-02-21: 6; 2023-02-22: 6; 2023-02-23: B; 2023-02-24: B; 2023-02-27: B; 2023-02-28: 7; 2023-03-01: 7; 2023-03-02: 7; 2023-03-03: 8; 2023-03-06: 8; 2023-03-07: 8; 2023-03-08: B; 2023-03-09: B; 2023-03-10: B; 2023-03-13: 9; 2023-03-14: 9; 2023-03-15: 9; 2023-03-16: 10; 2023-03-17: 10; 2023-03-20: 10; 2023-03-21: 11; 2023-03-22: 11; 2023-03-23: 11; 2023-03-24: 12; 2023-03-27: 12; 2023-03-28: 12; 2023-03-29: 13; 2023-03-30: 13; 2023-03-31: 13; 2023-04-03: B; 2023-04-04: B; 2023-04-05: B; 2023-04-06: 14; 2023-04-07: 14; 2023-04-10: 14; 2023-04-11: 15; 2023-04-12: 15; 2023-04-13: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
10 | Install Electrical Fixtures & Mech Ceiling Drops |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-02-01: ZONE 2G; 2023-02-02: 1; 2023-02-03: 1; 2023-02-06: 1; 2023-02-07: 2; 2023-02-08: 2; 2023-02-09: 2; 2023-02-10: 3; 2023-02-13: 3; 2023-02-14: 3; 2023-02-15: 4; 2023-02-16: 4; 2023-02-17: 4; 2023-02-20: 5; 2023-02-21: 5; 2023-02-22: 5; 2023-02-23: 6; 2023-02-24: 6; 2023-02-27: 6; 2023-02-28: B; 2023-03-01: B; 2023-03-02: B; 2023-03-03: 7; 2023-03-06: 7; 2023-03-07: 7; 2023-03-08: 8; 2023-03-09: 8; 2023-03-10: 8; 2023-03-13: B; 2023-03-14: B; 2023-03-15: B; 2023-03-16: 9; 2023-03-17: 9; 2023-03-20: 9; 2023-03-21: 10; 2023-03-22: 10; 2023-03-23: 10; 2023-03-24: 11; 2023-03-27: 11; 2023-03-28: 11; 2023-03-29: 12; 2023-03-30: 12; 2023-03-31: 12; 2023-04-03: 13; 2023-04-04: 13; 2023-04-05: 13; 2023-04-06: B; 2023-04-07: B; 2023-04-10: B; 2023-04-11: 14; 2023-04-12: 14; 2023-04-13: 14; 2023-04-14: 15; 2023-04-17: 15; 2023-04-18: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
11 | Remaining Ceiling Drops & Install Casework |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-02-06: ZONE 2H; 2023-02-07: 1; 2023-02-08: 1; 2023-02-09: 1; 2023-02-10: 2; 2023-02-13: 2; 2023-02-14: 2; 2023-02-15: 3; 2023-02-16: 3; 2023-02-17: 3; 2023-02-20: 4; 2023-02-21: 4; 2023-02-22: 4; 2023-02-23: 5; 2023-02-24: 5; 2023-02-27: 5; 2023-02-28: 6; 2023-03-01: 6; 2023-03-02: 6; 2023-03-03: B; 2023-03-06: B; 2023-03-07: B; 2023-03-08: 7; 2023-03-09: 7; 2023-03-10: 7; 2023-03-13: 8; 2023-03-14: 8; 2023-03-15: 8; 2023-03-16: B; 2023-03-17: B; 2023-03-20: B; 2023-03-21: 9; 2023-03-22: 9; 2023-03-23: 9; 2023-03-24: 10; 2023-03-27: 10; 2023-03-28: 10; 2023-03-29: 11; 2023-03-30: 11; 2023-03-31: 11; 2023-04-03: 12; 2023-04-04: 12; 2023-04-05: 12; 2023-04-06: 13; 2023-04-07: 13; 2023-04-10: 13; 2023-04-11: B; 2023-04-12: B; 2023-04-13: B; 2023-04-14: 14; 2023-04-17: 14; 2023-04-18: 14; 2023-04-19: 15; 2023-04-20: 15; 2023-04-21: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
12 | Countertops, Millwork & Final Paint |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-02-09: ZONE 2I; 2023-02-10: 1; 2023-02-13: 1; 2023-02-14: 1; 2023-02-15: 2; 2023-02-16: 2; 2023-02-17: 2; 2023-02-20: 3; 2023-02-21: 3; 2023-02-22: 3; 2023-02-23: 4; 2023-02-24: 4; 2023-02-27: 4; 2023-02-28: 5; 2023-03-01: 5; 2023-03-02: 5; 2023-03-03: 6; 2023-03-06: 6; 2023-03-07: 6; 2023-03-08: B; 2023-03-09: B; 2023-03-10: B; 2023-03-13: 7; 2023-03-14: 7; 2023-03-15: 7; 2023-03-16: 8; 2023-03-17: 8; 2023-03-20: 8; 2023-03-21: B; 2023-03-22: B; 2023-03-23: B; 2023-03-24: 9; 2023-03-27: 9; 2023-03-28: 9; 2023-03-29: 10; 2023-03-30: 10; 2023-03-31: 10; 2023-04-03: 11; 2023-04-04: 11; 2023-04-05: 11; 2023-04-06: 12; 2023-04-07: 12; 2023-04-10: 12; 2023-04-11: 13; 2023-04-12: 13; 2023-04-13: 13; 2023-04-14: B; 2023-04-17: B; 2023-04-18: B; 2023-04-19: 14; 2023-04-20: 14; 2023-04-21: 14; 2023-04-24: 15; 2023-04-25: 15; 2023-04-26: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
13 | Wall & Casework Fixtures, Ceiling Tiles & Flooring |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-02-14: ZONE 2J; 2023-02-15: 1; 2023-02-16: 1; 2023-02-17: 1; 2023-02-20: 2; 2023-02-21: 2; 2023-02-22: 2; 2023-02-23: 3; 2023-02-24: 3; 2023-02-27: 3; 2023-02-28: 4; 2023-03-01: 4; 2023-03-02: 4; 2023-03-03: 5; 2023-03-06: 5; 2023-03-07: 5; 2023-03-08: 6; 2023-03-09: 6; 2023-03-10: 6; 2023-03-13: B; 2023-03-14: B; 2023-03-15: B; 2023-03-16: 7; 2023-03-17: 7; 2023-03-20: 7; 2023-03-21: 8; 2023-03-22: 8; 2023-03-23: 8; 2023-03-24: B; 2023-03-27: B; 2023-03-28: B; 2023-03-29: 9; 2023-03-30: 9; 2023-03-31: 9; 2023-04-03: 10; 2023-04-04: 10; 2023-04-05: 10; 2023-04-06: 11; 2023-04-07: 11; 2023-04-10: 11; 2023-04-11: 12; 2023-04-12: 12; 2023-04-13: 12; 2023-04-14: 13; 2023-04-17: 13; 2023-04-18: 13; 2023-04-19: B; 2023-04-20: B; 2023-04-21: B; 2023-04-24: 14; 2023-04-25: 14; 2023-04-26: 14; 2023-04-27: 15; 2023-04-28: 15; 2023-05-01: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
14 | Flooring, Final Paint & 1st Clean |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-02-17: ZONE 2K; 2023-02-20: 1; 2023-02-21: 1; 2023-02-22: 1; 2023-02-23: 2; 2023-02-24: 2; 2023-02-27: 2; 2023-02-28: 3; 2023-03-01: 3; 2023-03-02: 3; 2023-03-03: 4; 2023-03-06: 4; 2023-03-07: 4; 2023-03-08: 5; 2023-03-09: 5; 2023-03-10: 5; 2023-03-13: 6; 2023-03-14: 6; 2023-03-15: 6; 2023-03-16: B; 2023-03-17: B; 2023-03-20: B; 2023-03-21: 7; 2023-03-22: 7; 2023-03-23: 7; 2023-03-24: 8; 2023-03-27: 8; 2023-03-28: 8; 2023-03-29: B; 2023-03-30: B; 2023-03-31: B; 2023-04-03: 9; 2023-04-04: 9; 2023-04-05: 9; 2023-04-06: 10; 2023-04-07: 10; 2023-04-10: 10; 2023-04-11: 11; 2023-04-12: 11; 2023-04-13: 11; 2023-04-14: 12; 2023-04-17: 12; 2023-04-18: 12; 2023-04-19: 13; 2023-04-20: 13; 2023-04-21: 13; 2023-04-24: B; 2023-04-25: B; 2023-04-26: B; 2023-04-27: 14; 2023-04-28: 14; 2023-05-01: 14; 2023-05-02: 15; 2023-05-03: 15; 2023-05-04: 15; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
15 | Punchlist, Corrections & Final Clean | bar: 2022-05-30; 2022-07-04; 2022-09-07; 2022-11-22 to 2022-11-25; 2022-12-26 to 2022-12-27; 2023-05-29; 2023-07-04; 2023-09-05
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [40 empty] | ZONE 3A | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [13 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [43 empty] | ZONE 3B | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [10 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [46 empty] | ZONE 3C | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [7 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [49 empty] | ZONE 3D | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 |  |  |  |  | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [52 empty] | ZONE 3E | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 |  | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [55 empty] | ZONE 4A | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | H | 15 | 15 | [23 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [58 empty] | ZONE 4B | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | H | 14 | 14 | 15 | 15 | 15 | [20 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [61 empty] | ZONE 4C | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | H | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [17 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [64 empty] | ZONE 4D | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | H | 13 | 13 | B | B | B | 14 | 14 | 14 | 15 | 15 | 15 | [14 empty] | H | [44 empty] | H
EXTERIOR LEGEND |  |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-03-31: ZONE 4E; 2023-04-03: 1; 2023-04-04: 1; 2023-04-05: 1; 2023-04-06: 2; 2023-04-07: 2; 2023-04-10: 2; 2023-04-11: 3; 2023-04-12: 3; 2023-04-13: 3; 2023-04-14: 4; 2023-04-17: 4; 2023-04-18: 4; 2023-04-19: 5; 2023-04-20: 5; 2023-04-21: 5; 2023-04-24: 6; 2023-04-25: 6; 2023-04-26: 6; 2023-04-27: B; 2023-04-28: B; 2023-05-01: B; 2023-05-02: 7; 2023-05-03: 7; 2023-05-04: 7; 2023-05-05: 8; 2023-05-08: 8; 2023-05-09: 8; 2023-05-10: B; 2023-05-11: B; 2023-05-12: B; 2023-05-15: 9; 2023-05-16: 9; 2023-05-17: 9; 2023-05-18: 10; 2023-05-19: 10; 2023-05-22: 10; 2023-05-23: 11; 2023-05-24: 11; 2023-05-25: 11; 2023-05-26: 12; 2023-05-29: H; 2023-05-30: 12; 2023-05-31: 12; 2023-06-01: 13; 2023-06-02: 13; 2023-06-05: 13; 2023-06-06: B; 2023-06-07: B; 2023-06-08: B; 2023-06-09: 14; 2023-06-12: 14; 2023-06-13: 14; 2023-06-14: 15; 2023-06-15: 15; 2023-06-16: 15; 2023-07-04: H; 2023-09-05: H
A | Structural Steel Supports |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-04-05: ZONE 4F; 2023-04-06: 1; 2023-04-07: 1; 2023-04-10: 1; 2023-04-11: 2; 2023-04-12: 2; 2023-04-13: 2; 2023-04-14: 3; 2023-04-17: 3; 2023-04-18: 3; 2023-04-19: 4; 2023-04-20: 4; 2023-04-21: 4; 2023-04-24: 5; 2023-04-25: 5; 2023-04-26: 5; 2023-04-27: 6; 2023-04-28: 6; 2023-05-01: 6; 2023-05-02: B; 2023-05-03: B; 2023-05-04: B; 2023-05-05: 7; 2023-05-08: 7; 2023-05-09: 7; 2023-05-10: 8; 2023-05-11: 8; 2023-05-12: 8; 2023-05-15: B; 2023-05-16: B; 2023-05-17: B; 2023-05-18: 9; 2023-05-19: 9; 2023-05-22: 9; 2023-05-23: 10; 2023-05-24: 10; 2023-05-25: 10; 2023-05-26: 11; 2023-05-29: H; 2023-05-30: 11; 2023-05-31: 11; 2023-06-01: 12; 2023-06-02: 12; 2023-06-05: 12; 2023-06-06: 13; 2023-06-07: 13; 2023-06-08: 13; 2023-06-09: B; 2023-06-12: B; 2023-06-13: B; 2023-06-14: 14; 2023-06-15: 14; 2023-06-16: 14; 2023-06-19: 15; 2023-06-20: 15; 2023-06-21: 15; 2023-07-04: H; 2023-09-05: H
B | Framing & Sheathing |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-04-10: ZONE 4G; 2023-04-11: 1; 2023-04-12: 1; 2023-04-13: 1; 2023-04-14: 2; 2023-04-17: 2; 2023-04-18: 2; 2023-04-19: 3; 2023-04-20: 3; 2023-04-21: 3; 2023-04-24: 4; 2023-04-25: 4; 2023-04-26: 4; 2023-04-27: 5; 2023-04-28: 5; 2023-05-01: 5; 2023-05-02: 6; 2023-05-03: 6; 2023-05-04: 6; 2023-05-05: B; 2023-05-08: B; 2023-05-09: B; 2023-05-10: 7; 2023-05-11: 7; 2023-05-12: 7; 2023-05-15: 8; 2023-05-16: 8; 2023-05-17: 8; 2023-05-18: B; 2023-05-19: B; 2023-05-22: B; 2023-05-23: 9; 2023-05-24: 9; 2023-05-25: 9; 2023-05-26: 10; 2023-05-29: H; 2023-05-30: 10; 2023-05-31: 10; 2023-06-01: 11; 2023-06-02: 11; 2023-06-05: 11; 2023-06-06: 12; 2023-06-07: 12; 2023-06-08: 12; 2023-06-09: 13; 2023-06-12: 13; 2023-06-13: 13; 2023-06-14: B; 2023-06-15: B; 2023-06-16: B; 2023-06-19: 14; 2023-06-20: 14; 2023-06-21: 14; 2023-06-22: 15; 2023-06-23: 15; 2023-06-26: 15; 2023-07-04: H; 2023-09-05: H
C | EIFS |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-04-13: ZONE 4H; 2023-04-14: 1; 2023-04-17: 1; 2023-04-18: 1; 2023-04-19: 2; 2023-04-20: 2; 2023-04-21: 2; 2023-04-24: 3; 2023-04-25: 3; 2023-04-26: 3; 2023-04-27: 4; 2023-04-28: 4; 2023-05-01: 4; 2023-05-02: 5; 2023-05-03: 5; 2023-05-04: 5; 2023-05-05: 6; 2023-05-08: 6; 2023-05-09: 6; 2023-05-10: B; 2023-05-11: B; 2023-05-12: B; 2023-05-15: 7; 2023-05-16: 7; 2023-05-17: 7; 2023-05-18: 8; 2023-05-19: 8; 2023-05-22: 8; 2023-05-23: B; 2023-05-24: B; 2023-05-25: B; 2023-05-26: 9; 2023-05-29: H; 2023-05-30: 9; 2023-05-31: 9; 2023-06-01: 10; 2023-06-02: 10; 2023-06-05: 10; 2023-06-06: 11; 2023-06-07: 11; 2023-06-08: 11; 2023-06-09: 12; 2023-06-12: 12; 2023-06-13: 12; 2023-06-14: 13; 2023-06-15: 13; 2023-06-16: 13; 2023-06-19: B; 2023-06-20: B; 2023-06-21: B; 2023-06-22: 14; 2023-06-23: 14; 2023-06-26: 14; 2023-06-27: 15; 2023-06-28: 15; 2023-06-29: 15; 2023-07-04: H; 2023-09-05: H
D | Window Installation |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-10-18: B; 2022-10-19: B; 2022-10-20: B; 2022-10-21: B; 2022-10-24: B; 2022-10-25: B; 2022-10-26: B; 2022-10-27: B; 2022-10-28: B; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-04-18: ZONE 4I; 2023-04-19: 1; 2023-04-20: 1; 2023-04-21: 1; 2023-04-24: 2; 2023-04-25: 2; 2023-04-26: 2; 2023-04-27: 3; 2023-04-28: 3; 2023-05-01: 3; 2023-05-02: 4; 2023-05-03: 4; 2023-05-04: 4; 2023-05-05: 5; 2023-05-08: 5; 2023-05-09: 5; 2023-05-10: 6; 2023-05-11: 6; 2023-05-12: 6; 2023-05-15: B; 2023-05-16: B; 2023-05-17: B; 2023-05-18: 7; 2023-05-19: 7; 2023-05-22: 7; 2023-05-23: 8; 2023-05-24: 8; 2023-05-25: 8; 2023-05-26: B; 2023-05-29: H; 2023-05-30: B; 2023-05-31: B; 2023-06-01: 9; 2023-06-02: 9; 2023-06-05: 9; 2023-06-06: 10; 2023-06-07: 10; 2023-06-08: 10; 2023-06-09: 11; 2023-06-12: 11; 2023-06-13: 11; 2023-06-14: 12; 2023-06-15: 12; 2023-06-16: 12; 2023-06-19: 13; 2023-06-20: 13; 2023-06-21: 13; 2023-06-22: B; 2023-06-23: B; 2023-06-26: B; 2023-06-27: 14; 2023-06-28: 14; 2023-06-29: 14; 2023-06-30: 15; 2023-07-03: 15; 2023-07-04: H; 2023-07-05: 15; 2023-09-05: H
E | Final Caulking & Finishes |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-10-28: EAST A; 2022-10-31: A; 2022-11-01: A; 2022-11-02: A; 2022-11-03: A; 2022-11-04: A; 2022-11-07: B; 2022-11-08: B; 2022-11-09: B; 2022-11-10: B; 2022-11-11: B; 2022-11-14: B; 2022-11-15: B; 2022-11-16: B; 2022-11-17: B; 2022-11-18: B; 2022-11-21: C; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-11-28: C; 2022-11-29: C; 2022-11-30: C; 2022-12-01: C; 2022-12-02: D; 2022-12-05: D; 2022-12-06: D; 2022-12-07: D; 2022-12-08: D; 2022-12-09: E; 2022-12-12: E; 2022-12-13: E; 2022-12-14: E; 2022-12-15: E; 2022-12-26: H; 2022-12-27: H; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
F | Shade Structure |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-04: EAST B; 2022-11-07: A; 2022-11-08: A; 2022-11-09: A; 2022-11-10: A; 2022-11-11: A; 2022-11-14: B; 2022-11-15: B; 2022-11-16: B; 2022-11-17: B; 2022-11-18: B; 2022-11-21: B; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-11-28: B; 2022-11-29: B; 2022-11-30: B; 2022-12-01: B; 2022-12-02: C; 2022-12-05: C; 2022-12-06: C; 2022-12-07: C; 2022-12-08: C; 2022-12-09: D; 2022-12-12: D; 2022-12-13: D; 2022-12-14: D; 2022-12-15: D; 2022-12-16: E; 2022-12-19: E; 2022-12-20: E; 2022-12-21: E; 2022-12-22: E; 2022-12-26: H; 2022-12-27: H; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [46 empty] | EAST C | A | A | A | A | A | B | H | H | H | H | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | H | H | E | E | E | E | [78 empty] | ZONE 5A | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | H | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | 14 | 14 | H | 14 | 15 | 15 | 15 | [40 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [51 empty] | EAST D | A | H | H | H | H | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | H | H | D | D | D | D | E | E | E | E | E | [76 empty] | ZONE 5B | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | H | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | B | B | H | B | 14 | 14 | 14 | 15 | 15 | 15 | B | B | [35 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H |  |  |  | SOUTH A | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | H | H | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [94 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [8 empty] | SOUTH B | A | A | A | A | A | B | B | B | B | B | B | H | H | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [89 empty] | H | [25 empty] | H | [44 empty] | H
FINISHING SITEWORK LEGEND |  |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-15: SOUTH C; 2022-12-16: A; 2022-12-19: A; 2022-12-20: A; 2022-12-21: A; 2022-12-22: A; 2022-12-23: B; 2022-12-26: H; 2022-12-27: H; 2022-12-28: B; 2022-12-29: B; 2022-12-30: B; 2023-01-02: B; 2023-01-03: B; 2023-01-04: B; 2023-01-05: B; 2023-01-06: B; 2023-01-09: B; 2023-01-10: C; 2023-01-11: C; 2023-01-12: C; 2023-01-13: C; 2023-01-16: C; 2023-01-17: D; 2023-01-18: D; 2023-01-19: D; 2023-01-20: D; 2023-01-23: D; 2023-01-24: E; 2023-01-25: E; 2023-01-26: E; 2023-01-27: E; 2023-01-30: E; 2023-01-31: B; 2023-02-01: B; 2023-02-02: B; 2023-02-03: B; 2023-02-06: B; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
1 | Site Demoblization |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-22: SOUTH D; 2022-12-23: A; 2022-12-26: H; 2022-12-27: H; 2022-12-28: A; 2022-12-29: A; 2022-12-30: A; 2023-01-02: A; 2023-01-03: B; 2023-01-04: B; 2023-01-05: B; 2023-01-06: B; 2023-01-09: B; 2023-01-10: B; 2023-01-11: B; 2023-01-12: B; 2023-01-13: B; 2023-01-16: B; 2023-01-17: C; 2023-01-18: C; 2023-01-19: C; 2023-01-20: C; 2023-01-23: C; 2023-01-24: D; 2023-01-25: D; 2023-01-26: D; 2023-01-27: D; 2023-01-30: D; 2023-01-31: E; 2023-02-01: E; 2023-02-02: E; 2023-02-03: E; 2023-02-06: E; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
2 | UG Electrical |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-02: WEST A; 2023-01-03: A; 2023-01-04: A; 2023-01-05: A; 2023-01-06: A; 2023-01-09: A; 2023-01-10: B; 2023-01-11: B; 2023-01-12: B; 2023-01-13: B; 2023-01-16: B; 2023-01-17: B; 2023-01-18: B; 2023-01-19: B; 2023-01-20: B; 2023-01-23: B; 2023-01-24: C; 2023-01-25: C; 2023-01-26: C; 2023-01-27: C; 2023-01-30: C; 2023-01-31: D; 2023-02-01: D; 2023-02-02: D; 2023-02-03: D; 2023-02-06: D; 2023-02-07: E; 2023-02-08: E; 2023-02-09: E; 2023-02-10: E; 2023-02-13: E; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
3 | Rough Grading |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-09: WEST B; 2023-01-10: A; 2023-01-11: A; 2023-01-12: A; 2023-01-13: A; 2023-01-16: A; 2023-01-17: B; 2023-01-18: B; 2023-01-19: B; 2023-01-20: B; 2023-01-23: B; 2023-01-24: B; 2023-01-25: B; 2023-01-26: B; 2023-01-27: B; 2023-01-30: B; 2023-01-31: C; 2023-02-01: C; 2023-02-02: C; 2023-02-03: C; 2023-02-06: C; 2023-02-07: D; 2023-02-08: D; 2023-02-09: D; 2023-02-10: D; 2023-02-13: D; 2023-02-14: E; 2023-02-15: E; 2023-02-16: E; 2023-02-17: E; 2023-02-20: E; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
4 | Hardscaping |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-16: WEST C; 2023-01-17: A; 2023-01-18: A; 2023-01-19: A; 2023-01-20: A; 2023-01-23: A; 2023-01-24: B; 2023-01-25: B; 2023-01-26: B; 2023-01-27: B; 2023-01-30: B; 2023-01-31: B; 2023-02-01: B; 2023-02-02: B; 2023-02-03: B; 2023-02-06: B; 2023-02-07: C; 2023-02-08: C; 2023-02-09: C; 2023-02-10: C; 2023-02-13: C; 2023-02-14: D; 2023-02-15: D; 2023-02-16: D; 2023-02-17: D; 2023-02-20: D; 2023-02-21: E; 2023-02-22: E; 2023-02-23: E; 2023-02-24: E; 2023-02-27: E; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
5 | Trees & Irrigation |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-23: WEST D; 2023-01-24: A; 2023-01-25: A; 2023-01-26: A; 2023-01-27: A; 2023-01-30: A; 2023-01-31: B; 2023-02-01: B; 2023-02-02: B; 2023-02-03: B; 2023-02-06: B; 2023-02-07: B; 2023-02-08: B; 2023-02-09: B; 2023-02-10: B; 2023-02-13: B; 2023-02-14: C; 2023-02-15: C; 2023-02-16: C; 2023-02-17: C; 2023-02-20: C; 2023-02-21: D; 2023-02-22: D; 2023-02-23: D; 2023-02-24: D; 2023-02-27: D; 2023-02-28: E; 2023-03-01: E; 2023-03-02: E; 2023-03-03: E; 2023-03-06: E; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
6 | Landscaping |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-01-30: NORTH A; 2023-01-31: A; 2023-02-01: A; 2023-02-02: A; 2023-02-03: A; 2023-02-06: A; 2023-02-07: B; 2023-02-08: B; 2023-02-09: B; 2023-02-10: B; 2023-02-13: B; 2023-02-14: B; 2023-02-15: B; 2023-02-16: B; 2023-02-17: B; 2023-02-20: B; 2023-02-21: C; 2023-02-22: C; 2023-02-23: C; 2023-02-24: C; 2023-02-27: C; 2023-02-28: D; 2023-03-01: D; 2023-03-02: D; 2023-03-03: D; 2023-03-06: D; 2023-03-07: E; 2023-03-08: E; 2023-03-09: E; 2023-03-10: E; 2023-03-13: E; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
7 | Paving |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-02-06: NORTH B; 2023-02-07: A; 2023-02-08: A; 2023-02-09: A; 2023-02-10: A; 2023-02-13: A; 2023-02-14: B; 2023-02-15: B; 2023-02-16: B; 2023-02-17: B; 2023-02-20: B; 2023-02-21: B; 2023-02-22: B; 2023-02-23: B; 2023-02-24: B; 2023-02-27: B; 2023-02-28: C; 2023-03-01: C; 2023-03-02: C; 2023-03-03: C; 2023-03-06: C; 2023-03-07: D; 2023-03-08: D; 2023-03-09: D; 2023-03-10: D; 2023-03-13: D; 2023-03-14: E; 2023-03-15: E; 2023-03-16: E; 2023-03-17: E; 2023-03-20: E; 2023-05-29: H; 2023-07-04: H; 2023-09-05: H
8 | Site Finishes |  | 2022-05-30: H; 2022-07-04: H; 2022-09-07: H; 2022-11-22: H; 2022-11-23: H; 2022-11-24: H; 2022-11-25: H; 2022-12-26: H; 2022-12-27: H; 2023-02-13: NORTH C; 2023-02-14: A; 2023-02-15: A; 2023-02-16: A; 2023-02-17: A; 2023-02-20: A; 2023-02-21: B; 2023-02-22: B; 2023-02-23: B; 2023-02-24: B; 2023-02-27: B; 2023-02-28: B; 2023-03-01: B; 2023-03-02: B; 2023-03-03: B; 2023-03-06: B; 2023-03-07: C; 2023-03-08: C; 2023-03-09: C; 2023-03-10: C; 2023-03-13: C; 2023-03-14: D; 2023-03-15: D; 2023-03-16: D; 2023-03-17: D; 2023-03-20: D; 2023-03-21: E; 2023-03-22: E; 2023-03-23: E; 2023-03-24: E; 2023-03-27: E; 2023-05-29: H; 2023-06-08: Pre-functional Checklists; 2023-07-04: H; 2023-09-05: H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [38 empty] | NORTH D | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [39 empty] | H | [18 empty] | Controls | [6 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [8 empty] | TAB | [35 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [17 empty] | Cx + FA Testing | [10 empty] | B | B | B | B | B | B | B | B | B | B | [6 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [69 empty] | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | F | [14 empty] | H | [25 empty] | H | [17 empty] | LS/ FA Testing | [26 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H |  |  |  |  | B | B | B | B | B | [15 empty] | Roofing Area A | [83 empty] | H | [25 empty] | H | [27 empty] | Functional Performance Testing | [16 empty] | H |  |  |  | B | B | B | B | B | B | B | B | B | B
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [39 empty] | Roofing Area B | [68 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [48 empty] | Set AHU | [59 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [58 empty] | Mechanical Installation | [49 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [68 empty] | Controls | [24 empty] | AREA A | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | H | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 |  |  |  |  | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [78 empty] | Point to Point | [19 empty] | AREA B | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | H | 2 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | H | 8 | [43 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [83 empty] | Mech Startup | [19 empty] | AREA C | 1 | 1 | 1 | 1 | H | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | H | 7 | 8 | 8 | 8 | 8 | 8 | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | [6 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[83 empty] | H | [24 empty] | H | [46 empty] | H | [53 empty] | H | H | H | H | [20 empty] | H | H | [108 empty] | H | [25 empty] | H | [44 empty] | H
[242 empty] | ZONE 2A | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[245 empty] | ZONE 2B | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[209 empty] | S4 | S4 | S4 | S4 | [35 empty] | ZONE 2C | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[209 empty] | S4 | S4 | S4 | S4 | [38 empty] | ZONE 2D | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[209 empty] | S4 | S4 | S4 | S4 | [41 empty] | ZONE 2E | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[257 empty] | ZONE 2F | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[260 empty] | ZONE 2G | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[263 empty] | ZONE 2H | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[266 empty] | ZONE 2I | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[269 empty] | ZONE 2J | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[272 empty] | ZONE 2K | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[209 empty] | B | B | B | B
Interiors Phase
Exteriors Phase
Structure Phase
Foundations Phase
Sitework Phase
Neuroscience Institute Takt Plan
Zone Map
POWER ON
AIR ON

## Logistics Plan
CURRENT WEEK | AREA/ZONE | CRANE | FORKLIFT | HOIST | MONDAY | CRANE | FORKLIFT | HOIST | TUESDAY | CRANE | FORKLIFT | HOIST | WEDNESDAY | CRANE | FORKLIFT | HOIST | THURSDAY | CRANE | FORKLIFT | HOIST | FRIDAY | CRANE | FORKLIFT | HOIST | SATURDAY
[5 empty] | DESCRIPTION |  |  |  | DESCRIPTION |  |  |  | DESCRIPTION |  |  |  | DESCRIPTION |  |  |  | DESCRIPTION |  |  |  | DESCRIPTION
5:00
6:00
7:00
8:00
9:00
10:00
11:00
12:00
13:00
14:00
15:00
16:00
17:00
18:00
19:00
NOTES:
LOGISTICS
DELIVERIES

## 6WLA
|  |  | 2023 |  |  |  |  | 2023 |  |  |  |  | 2023 |  |  |  |  | 2023 |  |  |  |  | 2023 |  |  |  |  | 2023
|  |  | January |  |  |  |  | January |  |  |  |  | January |  |  |  |  | February |  |  |  |  | February |  |  |  |  | February
|  |  | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24
|  |  | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
PRE-CON MEETINGS |  |  | 2023-02-03: South Exterioirs EIFS
[7 empty] | Level 2 Zone E&F Framing | [9 empty] | Level 3 Fire Sprinkler |  |  |  |  | Level 3 OH MEP
STAIRS & ELEVATORS | [32 empty] | STAIRS & ELEVATORS
| BUILDING |  | 2023-02-14: Shaft Prep | BUILDING
Erect Stair 2
|  |  | Pour 1 | [15 empty] | Pour 2
INTERIORS
INTERIORS | FLOOR 1 | Zone 1A | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | Zone 1A | FLOOR 1 | INTERIORS
|  | Zone 1B | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | Zone 1B
|  | Zone 1C | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | Zone 1C
| FLOOR 1 | Zone 2A |  | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | Zone 2A | FLOOR 1
|  | Zone 2B |  |  |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | 7 | 8 | 8 | Zone 2B
|  | Zone 2C | [7 empty] | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | 7 | 7 | Zone 2C
|  | Zone 2D | [10 empty] | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | Zone 2D
|  | Zone 2E | 2023-02-02: 1; 2023-02-03: 1; 2023-02-06: 1; 2023-02-07: 2; 2023-02-08: 2; 2023-02-09: 2; 2023-02-10: 3; 2023-02-13: 3; 2023-02-14: 3; 2023-02-15: 4; 2023-02-16: 4; 2023-02-17: 4; 2023-02-20: 5; 2023-02-21: 5; 2023-02-22: 5; 2023-02-23: 6; 2023-02-24: 6 | Zone 2E
|  | Zone 2F | 2023-02-07: 1; 2023-02-08: 1; 2023-02-09: 1; 2023-02-10: 2; 2023-02-13: 2; 2023-02-14: 2; 2023-02-15: 3; 2023-02-16: 3; 2023-02-17: 3; 2023-02-20: 4; 2023-02-21: 4; 2023-02-22: 4; 2023-02-23: 5; 2023-02-24: 5 | Zone 2F
|  | Zone 2G | 2023-02-10: 1; 2023-02-13: 1; 2023-02-14: 1; 2023-02-15: 2; 2023-02-16: 2; 2023-02-17: 2; 2023-02-20: 3; 2023-02-21: 3; 2023-02-22: 3; 2023-02-23: 4; 2023-02-24: 4 | Zone 2G
|  | Zone 2H | 2023-02-15: 1; 2023-02-16: 1; 2023-02-17: 1; 2023-02-20: 2; 2023-02-21: 2; 2023-02-22: 2; 2023-02-23: 3; 2023-02-24: 3 | Zone 2H
|  | Zone 2I | 2023-02-20: 1; 2023-02-21: 1; 2023-02-22: 1; 2023-02-23: 2; 2023-02-24: 2 | Zone 2I
|  | Zone 2J | [30 empty] | Zone 2J | bar: 2023-02-23 to 2023-02-24
EXTERIORS
EXTERIORS | WEST | Zone C | [30 empty] | Zone C | WEST | EXTERIORS | bar: 2023-01-16 to 2023-01-17
|  | Zone D | [30 empty] | Zone D | bar: 2023-01-16 to 2023-01-24
| EAST | Zone A | 2023-01-16: C; 2023-01-17: C; 2023-01-18: D; 2023-01-19: D; 2023-01-20: D; 2023-01-23: D; 2023-01-24: D; 2023-01-25: E; 2023-01-26: E; 2023-01-27: E; 2023-01-30: E; 2023-01-31: E | Zone A | EAST
|  | Zone B | 2023-01-16: B; 2023-01-17: B; 2023-01-18: C; 2023-01-19: C; 2023-01-20: C; 2023-01-23: C; 2023-01-24: C; 2023-01-25: D; 2023-01-26: D; 2023-01-27: D; 2023-01-30: D; 2023-01-31: D; 2023-02-01: E; 2023-02-02: E; 2023-02-03: E; 2023-02-06: E; 2023-02-07: E | Zone B
|  | Zone C | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E | [8 empty] | Zone C
|  | Zone D | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | E | E |  |  |  | Zone D
| NORTH | Zone A |  |  | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | D | D | E | E | E | Zone A | NORTH
|  | Zone B | [7 empty] | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | C | C | D | D | D | Zone B
|  | Zone C | [12 empty] | A | A | A | A | A | B | B | B | B | B | B | B | B | B | B | C | C | C | Zone C
|  | Zone D | [30 empty] | Zone D | bar: 2023-02-08 to 2023-02-24
| SOUTH | Zone A | [30 empty] | Zone A | SOUTH | bar: 2023-02-15 to 2023-02-24
|  | Zone B | [30 empty] | Zone B | bar: 2023-02-22 to 2023-02-24
WWP
WWP
WEEK 2
WEEK 3
WEEK 4
WEEK 5
WEEK 6
WEEK 2
WEEK 3
WEEK 4
WEEK 5
WEEK 6

## Weekly Work Plan (One Floor)
ASK QUESTIONS & HAVE A DISCUSSION 1. Ask where your bottleneck zone is 2. Ask what’s your slowest trades 3. Discuss any owner changes with the trades 4. Remind the team of any key project planning items 5. Discuss key handoffs for the next two days 6. Discuss any new activities starting 7. Discuss any quality meetings needed for new work 8. Discuss deliveries and ask where they go | [5 empty] | TRADE PARTNER WEEKLY TACTICAL 1. Make the weekly work plan: 1 - Week 2. Review last week 3. Review current week 4. Review current progress 5. Fill out any one-off activities
WEEKLY WORK PLAN (JAN 16-20) | [5 empty] | 16 | 17 | 18 | 19 | 20 | NOTES | PPC |  |  | SUCCESSFUL HANDOFF %
PHASE | FLOOR | ZONE | TRADE | # | ACTIVITY | M | T | W | T | F |  | Planned | Done | % | Planned | Completed
INTERIORS | FLOOR 1 | Zone 1A | Mechanical #1 | 3 | OH Mechanical Duct | H | [5 empty] | 1 | 1 | 100% | 12 | 11
|  |  | Mechanical #2 | 4 | OH Mech Equip, Piping, Branch Lines & Plumbing |  |  |  | H |  |  | 3 | 3 | 100%
|  |  | Electrical | 5 | OH Electrical & Frame Walls | [6 empty] | 1 | 0 | 0% | PHP = | 91.67%
|  | Zone 1B | FS | 2 | Install Fire Sprinkler Main and Branch Lines & Install Priority Walls | H | [5 empty] | 1 | 1 | 100%
|  |  | Mechanical #1 | 3 | OH Mechanical Duct |  |  |  | H |  |  | 3 | 3 | 100%
|  |  | Mechanical #2 | 4 | OH Mech Equip, Piping, Branch Lines & Plumbing | [6 empty] | 1 | 1 | 100%
|  | Zone 1C | Concrete | 1 | Remove re-shores, Floor Prep, Final Patch Ceiling & Layout Walls | H | [5 empty] | 1 | 1 | 100%
|  |  | FS | 2 | Install Fire Sprinkler Main and Branch Lines & Install Priority Walls |  |  |  | H |  |  | 3 | 3 | 100%
|  |  | Mechanical #1 | 3 | OH Mechanical Duct | [6 empty] | 1 | 1 | 100%
| FLOOR 2 | Zone 2A | Concrete | 1 | Remove re-shores, Floor Prep, Final Patch Ceiling & Layout Walls |  |  |  | H |  |  | 3 | 3 | 100%
|  |  | FS | 2 | Install Fire Sprinkler Main and Branch Lines & Install Priority Walls | [6 empty] | 1 | 1 | 100%
|  | Zone 2B | Concrete | 1 | Remove re-shores, Floor Prep, Final Patch Ceiling & Layout Walls | [6 empty] | 1 | 1 | 100%
WEEKLY WORK PLAN (JAN 16-20) | [5 empty] | 16 | 17 | 18 | 19 | 20 | NOTES | PPC
PHASE | FLOOR | ZONE | TRADE | # | ACTIVITY | M | T | W | T | F |  | Planned | Done | %
EXTERIORS | WEST | ZONE C | Finishers | E | Final Caulking & Finishes |  | H |  |  |  |  | 2 | 2 | 100%
|  | ZONE D | Glaziers | D | Window Installation |  | H |  |  |  |  | 2 | 2 | 100%
|  |  | Finishers | E | Final Caulking & Finishes | [6 empty] | 3 | 3 | 100%
| EAST | ZONE A | EIFS installers | C | EIFS |  | H |  |  |  |  | 2 | 1 | 50%
|  |  | Glaziers | D | Window Installation | [6 empty] | 3 | 3 | 100%
|  | ZONE B | Framers | B | Framing & Sheathing |  | H |  |  |  |  | 2 | 1 | 50%
|  |  | EIFS installers | C | EIFS | [6 empty] | 3 | 3 | 100%
|  | ZONE C | Framers | B | Framing & Sheathing | [6 empty] | 5 | 5 | 100%
|  | ZONE D | Steel Erectors | A | Structural Steel Supports |  | H |  |  |  |  | 2 | 2 | 100%
|  |  | Framers | B | Framing & Sheathing | [6 empty] | 3 | 3 | 100%
| NORTH | ZONE A | Steel Erectors | A | Structural Steel Supports | [6 empty] | 3 | 3 | 100%
[12 empty] | 50 | 47
[12 empty] | PPC = | 94%
Interior Legend
RR
Zone Map (Floor 2 interior)
Zone Maps (Exteriors)
Exteriors Legend

## Roadblocks
SOLVE PROBLEMS - By now you will have red markings everywhere on your boards and on Canva. Any of these that are issues that need to be solved now go on the issues board. - Once all issues are listed you can ids each of them and make assignments below. it is crucial that all assignments are sized in a way that they can be done the next day in that day. if they are bigger than that they go on the team scrum board.
Roadblock Tracking and Removal Log (ISSUES)
No. | Roadblock | Zone | Date Added | Affected Activity | Who is on Point | Classification | Corrective Action | Critical Date | Count Down (Days) | Date Resolved | Process Time | Score | RR | Actions | Dashboard
1 | Roadblock 1 | Zone 1 | 2024-01-10 | Activity X | Person 1 | Classification 4 |  | 2024-01-22 | 5 | 2024-01-15 | 5 | -7 | 7 |  | Roadblock < 7 Days to Critical | 3
2 | Roadblock 2 | Zone 2 | 2024-01-22 | Activity Y | Person 2 | General |  | 2024-02-22 | 29 | 2024-02-20 | 29 | -2 | 2 |  | Uncleared Roadblocks | 0
3 | Roadblock 3 | Zone 3 | 2024-02-23 | Activity Z | Person 3 | Design |  | 2024-04-15 | 34 | 2024-03-28 | 34 | -18 | 18 |  | Cleared Roadblocks | 3
[15 empty] | Average Process Time | 22.6667
[15 empty] | Score | -9
[15 empty] | Roadblock Removal Average | 9
[15 empty] | List for Who is on Point | List for Classification
[15 empty] | Person 1 | General
[15 empty] | Person 2 | MEP
[15 empty] | Person 3 | Design
[15 empty] | Person 4 | Classification 4
[15 empty] | Person 5 | Classification 5
Classification 6
[12 empty] | -9 | 9
Formulas:
Count Down (Days) = IFS([Date Added]="","",[Date Resolved]="",[Critical Date]-TODAY(),[Date Resolved]>0,[Date Resolved]-[Date Added])

## Day Plan
AFTERNOON FOREMAN HUDDLE 1. Make the day plan: 1 - Day 2. Review today 3. Discuss tomorrow 4. Fill out the day plan according to the agenda 5. Fill out any one-off activities
SHOUT OUTS | The Concrete crew is out to a great start. They are cleaning as they go when stripping. ¦ Fire Sprinkler Trade is killing it with material staging.
FEEDBACK | Ask crews for feedback on bathrooms and lunch area…
SAFETY FOCUS | Biggest safety focus is being careful around stripping operations and removing all nails from wood stripped.
PERMITS | Electrical contractor has a dig permit at South exterior starting at 8am. Sign-off required before beginning. ¦ Also, Structural Steel Contractor has a hot work permit at South Stair. No access and fire watch to stay 30 minutes later.
WEATHER | Clear and Sunny
DELIVERIES | Delivery of Duct on First Floor. Place in room designed on Logistics map.
DAY PLAN | Fire Sprinkler is starting in Zone 1. We have a first in place mockup inspection scheduled for Monday. Concrete continues in Zone 2.
DAY PLAN
Zone Map
Logistics Plan

## HIDDEN GRAPHICS (hidden)
Percentage | Scale
10% | 1
20% | 1
30% | 1
40% | 1
50% | 1
60% | 1
70% | 1
80% | 1
90% | 1
100% | 9
94%
Degrees | 2.9531 | 0
| X | Y
Start | 0 | 0
Finish | 0.98229 | 0.18738
Percentage | Scale
10% | 1
20% | 1
30% | 1
40% | 1
50% | 1
60% | 1
70% | 1
80% | 1
90% | 1
100% | 9
91.67%
Degrees | 2.8798
| X | Y
Start | 0 | 0
Finish | 0.96593 | 0.25882
|  |  | TOTAL END BUFFERS | 18
Percentage | Scale
10% | 1
20% | 1
30% | 1
40% | 1
50% | 1
60% | 1
70% | 1
80% | 1
90% | 1
100% | 9
1
Degrees | 3.1416
| X | Y
Start | 0 | 0
Finish | 1 | 1.2246e-16
94%
KPIs
92%
1.00

## KPIs
9
Roadblock Removal Average (RRA)
KPIs
94%
92%
1.00

## Scrum Board
TEAM SCRUM BOARD 1. Any issues needing to scale to the team will be put into the backlog column 2. What did you do yesterday? 3. What will you do today? 4. What is standing in your way? 5. How can we help you? 6. How can we make this fun?
TO DO | TO DO THIS WEEK | DO TODAY | DONE
SCRUM BOARD
Install Windows
Painting
Activity X

## One Floor Norm Example
2022 | [19 empty] | 2023 | [129 empty] | 2024 | [261 empty] | 2025 | [260 empty] | 2026 | [260 empty] | 2027
December | [19 empty] | January | [21 empty] | February | [19 empty] | March | [22 empty] | April | [19 empty] | May | [22 empty] | June | [21 empty] | January | [22 empty] | February | [20 empty] | March | [20 empty] | April | [21 empty] | May | [22 empty] | June | [19 empty] | July | [22 empty] | August | [21 empty] | September | [20 empty] | October | [22 empty] | November | [20 empty] | December | [21 empty] | January | [22 empty] | February | [19 empty] | March | [20 empty] | April | [21 empty] | May | [21 empty] | June | [20 empty] | July | [22 empty] | August | [20 empty] | September | [21 empty] | October | [22 empty] | November | [19 empty] | December | [22 empty] | January | [21 empty] | February | [19 empty] | March | [21 empty] | April | [21 empty] | May | [20 empty] | June | [21 empty] | July | [22 empty] | August | [20 empty] | September | [21 empty] | October | [21 empty] | November | [20 empty] | December | [22 empty] | January | [21 empty] | February | [19 empty] | March | [21 empty] | April | [21 empty] | May | [20 empty] | June | [21 empty] | July | [22 empty] | August | [20 empty] | September | [21 empty] | October | [21 empty] | November | [20 empty] | December
2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | time axis 2024-01-01 to 2027-12-31
M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | time axis 2024-01-01 to 2027-12-31
[30 empty] | Zone 1 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | B | B | B | B | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[33 empty] | Zone 2 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | B | B | B | B | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | B | B | B | B | 15 | 15 | 15
[10 empty] | 1 | Remove re-shores, Floor Prep, Final Patch Ceiling & Layout Walls | [18 empty] | Remove Reshores | [5 empty] | Zone 3 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | B | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | B | B | B | B | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 2 | Install Fire Sprinkler Main and Branch Lines & Install Priority Walls | [27 empty] | Zone 4 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | B | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | B | B | B | B | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 3 | OH Mechanical | [30 empty] | Zone 5 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | B | B | B | B | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | B | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 4 | OH Mechanical, OH Plumbing | [33 empty] | Zone 6 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | B | B | B | B | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | B | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 5 | OH Electrical & Frame Walls | [36 empty] | Zone 7 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | B | B | B | B | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | B | B | B | B | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 6 | In-wall Electrical & Plumbing | [39 empty] | Zone 8 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | B | B | B | B | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | B | B | B | B | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 7 | In-wall Piping, One-side Dry Wall & In-wall Inspection | [42 empty] | Zone 9 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | 3 | 3 | 3 | B | B | B | B | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | B | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 8 | Second Side Dry Wall, Insulation & Finish Walls | [45 empty] | Zone 10 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | B | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | B | B | B | B | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15
[10 empty] | 9 | Prime 1st & 2nd Coat Paint | [48 empty] | Zone 11 | 1 | 1 | 1 | 2 | 2 | 2 | B | B | B | B | B | B | B | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | B | B | B | B | 8 | 8 | 8 | B | B | B | 9 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | B | B | B | 12 | 12 | 12 | 13 | 13 | 13 | 14 | 14 | 14 | 15 | 15 | 15 | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B | B
[10 empty] | 10 | Ceiling Grid, Lights, Electrical Fixtures & Mechanical Ceiling Drops | [63 empty] | Start Drywall | [5 empty] | Power On | [26 empty] | Air On |  |  |  |  | Fianal Clean | [10 empty] | Additional Buffer or Time Gained | [16 empty] | Contractual Substantial Completion and Financial Target
[10 empty] | 11 | Casework & Final Pain (Possible) | [113 empty] | Target Substantial Completion | [5 empty] | Target Final Completion
[10 empty] | 12 | Millwork, Plumbing, Wall and Casework, Ceiling Tiles | [28 empty] | Erect Stair
[10 empty] | 13 | Flooring | [32 empty] | Pour Stair Pans
[10 empty] | 14 | Final Paint, Final Clean 1st Pass & Incomplete Worklist | [37 empty] | Erect Stair
[10 empty] | 15 | Arch Punchlist, Corrections & Final Clean | [41 empty] | Pour Stair Pans
[75 empty] | Temp Roof |  |  |  |  | Install Swing Stages
Set AHU & Install
Zone 1-4
[11 empty] | Weather Risk | [7 empty] | 3 | [77 empty] | Zone 5-8
[11 empty] | Manpower not available | [7 empty] | 5 | [83 empty] | Zone 9-11
[11 empty] | Procurement Issues | [7 empty] | 5 | [83 empty] | B | B | B | B | B
[11 empty] | Shortage in crew | [7 empty] | 2
[11 empty] | Contractor labor not ready | [7 empty] | 8 | [32 empty] | Shaft Prep
[11 empty] | Higher risk | [7 empty] | 8 | [36 empty] | Elevator Cabs
Test + Certification
Pre-Functional Checklists
Controls
TAB
Commissioning
Fire Life Safety
Final Walks
Interiors
Neuroscience Institute Takt Plan
Logistics Map
Zone Map
Start Here
Need Help in Reading this Takt Plan?
Scan QR Code Below With Smart Phone Camera
Risk Analysis
Interior Legend
6 Week Look Ahead
WWP