## Start Here
From: LeanTakt team
Download the free PDF

## Takt Elements
Project Name
2024 | [52 empty] | 2025
Cold Winter Months | [43 empty] | Cold Winter Months | [51 empty] | Cold Winter Months
JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
 | time axis 2024-01-01 to 2025-12-29
INTERIORS LEGEND
[43 empty] | SOIL DISTURBANCE PERMIT | [29 empty] | 1 | Wall Layout + Top Track
[46 empty] | MAKE SAFE UTILITIES | [26 empty] | 2 | Fire Sprinkler + Priority Walls
[48 empty] | MOBILIZATION | [24 empty] | 3 | OH Ductwork
[50 empty] | EXCAVATION | [5 empty] | BIM LEGEND | [16 empty] | 4 | OH Branch Conduits and Lighting
[51 empty] | SHORING | [5 empty] | Model Coordination | [15 empty] | 5 | OH Mechanical Piping
[53 empty] | PIERS |  |  |  | Prepare Shop Drawings + Layout Drawings | [15 empty] | 6 | OH Electrical
[57 empty] | Shop Drawing Approval | [15 empty] | 7 | Wall Framing
[42 empty] | UG BIM Coordination | [14 empty] | Prefabrication of Material | [15 empty] | 8 | In wall Rough-in
[73 empty] | 9 | Soffits + Ceilings
[39 empty] | Shaft Prep | [33 empty] | 10 | Soffit & Ceiling Rough
[43 empty] | Elevator Cabs | [29 empty] | 11 | Drywall
[57 empty] | Test + Certification | [15 empty] | 12 | Taping
[39 empty] | Erect Stair | [33 empty] | 13 | Prime + First Coat
[43 empty] | Pour Stair Pans | [29 empty] | 14 | Data Cabling
[73 empty] | 15 | Ceiling Grid
[41 empty] | Temp Roof |  |  |  |  | Install Swing Stages | [26 empty] | 16 | Casework + Doors
[50 empty] | Set AHU & Install | [22 empty] | 17 | MEP Trim / Light and Devices
[55 empty] | Roofing | [17 empty] | 18 | Flooring + Baseboards
[73 empty] | 19 | Final Paint
[73 empty] | 20 | Final Accessories
[46 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | [5 empty] | 21 | Pre-Punch & Clean
[73 empty] | 22 | Punchlist
More colors
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | B | 15 | 16 | PI
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 |  |  |  |  | B |  |  |  | 13 | 14 | IR | B | 16 | PI
[12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[14 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | [8 empty] | 13 | 14 | IR | 15 | 16 | PI
[15 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
[16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
[17 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[38 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[39 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[40 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[41 empty] | 1 | 2 | 3 | 4 | 5 | [9 empty] | 6 | 7 | 8 | 9 | 10 | [9 empty] | 11 | 12 | 13 | 14 | 15
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | A | B | C | D | E | F
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | A | B | C | D | E | F
[11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | A | B | C | D | E | F
[12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | A | B | C | D | E | F
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | A | B | C | D | E | F
[14 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [8 empty] | A | B | C | D | E | F
Interiors
Finishes
Logistics Map
LEVEL 3
LEVEL 2
LEVEL 1
TARGET SUBSTANTIAL COMPLETION
POWER ON
AC ON
4 Week Look Ahead
Color palettes You can copy these colors for your takt's format
Examples of how to format line items, trains or one-off activities
Shapes Use for Phase Titles, Maps Titles, Logic Ties, Milestones, etc.

## Flow Analysis (hidden)
Download the free PDF

## Macro Calculator
Takt Inputs | [8 empty] | Selected Macro
Takt Wagons |  | 25 | [6 empty] | New Wagons Count | 20
Takt Zones |  | 4 | [6 empty] | Adjusted Takt Zones | 5
Takt Time |  | 5 | [6 empty] | Takt Time | 5
Duration |  | 140 | [6 empty] | Duration | 120
Starting Takt Wagons | Takt Zones | Norm Takt Time | Takt Wagons Adjusted | Takt Level | Duration | Macro Duration | Realized Flow Potential | 4
1
25 | 2 | 10 | 50 | NAO | 260 | 255 | 16.92% |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
25 | 3 | 7 | 35 | NAO | 189 | 185 | 23.28% |  |  | 1
25 | 4 | 5 | 25 | Macro | 140 | 140 | 31.43% |  |  | 2
25 | 5 | 4 | 20 | Macro | 116 | 120 | 37.93% | x |  | 3
25 | 6 | 4 | 20 | Macro | 120 | 125 | 36.67% |  |  | 4
25 | 7 | 3 | 15 | Macro | 93 | 105 | 47.31% |  |  | 5
25 | 8 | 3 | 15 | Macro | 96 | 110 | 45.83% |  |  | 6
25 | 9 | 3 | 15 | Macro | 99 | 115 | 44.44% |  |  | 7
25 | 10 | 2 | 10 | NAO | 68 | 95 | 64.71% |  |  | 8
25 | 11 | 2 | 10 | NAO | 70 | 100 | 62.86% |  |  | 9
25 | 12 | 2 | 10 | NAO | 72 | 105 | 61.11% |  |  | 10
25 | 13 | 2 | 10 | NAO | 74 | 110 | 59.46% |  |  | 11
25 | 14 | 2 | 10 | NAO | 76 | 115 | 57.89% |  |  | 12
25 | 15 | 2 | 10 | NAO | 78 | 120 | 56.41% |  |  | 13
25 | 16 | 2 | 10 | NAO | 80 | 125 | 55% |  |  | 14
25 | 17 | 2 | 10 | NAO | 82 | 130 | 53.66% |  |  | 15
25 | 18 | 2 | 10 | NAO | 84 | 135 | 52.38% |  |  | 16
25 | 19 | 2 | 10 | NAO | 86 | 140 | 51.16% |  |  | 17
25 | 20 | 1 | 5 | NAO | 44 | 120 | 100% |  |  | 18
25 | 21 | 1 | 5 | NAO | 45 | 125 | 97.78% |  |  | 19
25 | 22 | 1 | 5 | NAO | 46 | 130 | 95.65% |  |  | 20
25 | 23 | 1 | 5 | NAO | 47 | 135 | 93.62%
25 | 24 | 1 | 5 | NAO | 48 | 140 | 91.67%
25 | 25 | 1 | 5 | NAO | 49 | 145 | 89.8%
25 | 26 | 1 | 5 | NAO | 50 | 150 | 88%
25 | 27 | 1 | 5 | NAO | 51 | 155 | 86.27% |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
25 | 28 | 1 | 5 | NAO | 52 | 160 | 84.62% |  |  | 1 | bar: 1; 44; 47
25 | 29 | 1 | 5 | NAO | 53 | 165 | 83.02% |  |  | 2 | bar: 2
25 | 30 | 1 | 5 | NAO | 54 | 170 | 81.48% |  |  | 3 | bar: 3
25 | 31 | 1 | 5 | NAO | 55 | 175 | 80% |  |  | 4 | bar: 4
25 | 32 | 1 | 5 | NAO | 56 | 180 | 78.57% |  |  | 5 | bar: 5
25 | 33 | 1 | 5 | NAO | 57 | 185 | 77.19% |  |  | 6
25 | 34 | 1 | 5 | NAO | 58 | 190 | 75.86% |  |  | 7
25 | 35 | 1 | 5 | NAO | 59 | 195 | 74.58% |  |  | 8
25 | 36 | 1 | 5 | NAO | 60 | 200 | 73.33% |  |  | 9
25 | 37 | 1 | 5 | NAO | 61 | 205 | 72.13% |  |  | 10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
Shortest Durations
| Best # Zones | Takt Time | Duration
| 20 | 1 | 44
First Macro Iteration/ Original Guess
1st Macro Iteration/Original Guess
Competitive and Fair Macro Simulation
NAO = Not an Option

## Full MACRO - Before Review
|  |  | 2022 | [51 empty] | 2023
|  |  | Cold Winter Months | [21 empty] | Hot Summer Months | [21 empty] | Cold Winter Months | [29 empty] | Hot Summer Months
|  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER
 | time axis 2022-01-03 to 2023-10-30
|  | MILESTONES | 2022-09-05: Exteriors Phase Pull Plan
[24 empty] | Sitework Complete | [10 empty] | Foundation Complete | [16 empty] | Structure complete | [18 empty] | Air On |  |  |  |  | Final Sitework Pull Plan | [7 empty] | Interior Complete
[29 empty] | Structure Phase Pull Plan | [16 empty] | Interiors Phase Pull Plan | [20 empty] | Power On | [5 empty] | Exterior Complete
|  | PROCUREMENT | 2022-08-22: Electrical Gear; 2023-01-30: SES Fit-out & Energize
HVAC Equipment
Windows
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[9 empty] | Entire Site | MOB |  | 1H | 1H | 1H | 1I | 1I | 1I | 1I | 1J | 1J | 1J | 1J | 1K | [25 empty] | H |  |  |  |  | H
BEGINNING SITEWORK WORK |  |  | 2022-05-23: ZONE A; 2022-05-30: F1; 2022-06-06: F1; 2022-06-13: F2; 2022-06-20: F2; 2022-06-27: F3; 2022-07-04: F3; 2022-07-11: F4; 2022-07-18: F4; 2022-07-25: F4; 2022-08-01: B; 2022-08-08: B; 2022-11-21: H; 2022-12-26: H
1H | Excavation/Grading |  | 2022-06-06: ZONE B; 2022-06-13: F1; 2022-06-20: F1; 2022-06-27: F2; 2022-07-04: F2; 2022-07-11: F3; 2022-07-18: F3; 2022-07-25: F4; 2022-08-01: F4; 2022-08-08: F4; 2022-08-15: B; 2022-08-22: B; 2022-11-21: H; 2022-12-26: H
1I | Install Storm/Sanitary/Water/Dry U.G. Utilities | bar: 2022-11-21; 2022-12-26
1J | Parking Area Base Stone | bar: 2022-11-21; 2022-12-26
1K | Final Grading |  | 2022-02-14: NTP; 2022-08-08: LEVEL 1; 2022-08-15: S1; 2022-08-22: S1; 2022-08-29: S1; 2022-09-05: S1; 2022-09-12: S2; 2022-09-19: S2; 2022-09-26: S2; 2022-10-03: S2; 2022-10-10: S3; 2022-10-17: S3; 2022-10-24: S4; 2022-10-31: S4; 2022-11-07: S4; 2022-11-21: H; 2022-12-26: H; 2023-08-21: Substantial Completion; 2023-09-18: Final Completion + Financial Completion
[35 empty] | LEVEL 2 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S3 | S3 | S4 | S4 | S4 | H |  |  |  |  | H
[36 empty] | LEVEL 3 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S3 | S3 | S4 | S4 | H | S4 |  |  |  | H
[37 empty] | LEVEL 4 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S3 | S3 | S4 | H | S4 | S4 |  |  | H
FOUNDATION LEGEND |  |  | 2022-09-05: LEVEL 5; 2022-09-12: S1; 2022-09-19: S1; 2022-09-26: S1; 2022-10-03: S1; 2022-10-10: S2; 2022-10-17: S2; 2022-10-24: S2; 2022-10-31: S2; 2022-11-07: S3; 2022-11-14: S3; 2022-11-21: H; 2022-11-28: S4; 2022-12-05: S4; 2022-12-12: S4; 2022-12-26: H
F1 | Excavate & Pour Footings | bar: 2022-11-21; 2022-12-26
F2 | Columns & Walls | bar: 2022-11-21; 2022-12-26
F3 | UG MEP | bar: 2022-11-21; 2022-12-26
F4 | SOG | bar: 2022-11-21; 2022-12-26
B | Buffer | bar: 2022-11-21; 2022-12-26
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  | ZONE 1A | 1 | H | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
STRUCTURE LEGEND | [48 empty] | H |  |  |  | ZONE 1B | H | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
S1 | Deck Formwork | [47 empty] | H |  |  |  |  | H
S2 | Deck MEP & Reinforcing | [47 empty] | H | [5 empty] | ZONE 2A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
S3 | Deck Inspections & Place | [47 empty] | H | [6 empty] | ZONE 2B | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
S4 | Columns & Walls | [47 empty] | H |  |  |  |  | H |  |  | ZONE 2C | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H |  |  |  | ZONE 2D | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H |  |  |  |  | ZONE 2E | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H | [5 empty] | ZONE 3A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
EXTERIOR LEGEND | [48 empty] | H |  |  |  |  | H | [6 empty] | ZONE 3B | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
A | Structural Steel Supports | [47 empty] | H |  |  |  |  | H | [7 empty] | ZONE 3C | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
B | Framing & Sheathing | [47 empty] | H |  |  |  |  | H
C | EIFS | [47 empty] | H |  |  |  |  | H | [8 empty] | ZONE 4A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D | Window Installation | [47 empty] | H |  |  |  |  | H | [9 empty] | ZONE 4B | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
E | Final Caulking & Finishes | [47 empty] | H |  |  |  |  | H | [10 empty] | ZONE 4C | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
F | Shade Structure | [47 empty] | H |  |  |  |  | H | [11 empty] | ZONE 4D | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H | [12 empty] | ZONE 5A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | B
[49 empty] | H |  |  |  |  | H
INTERIOR LEGEND | [48 empty] | H |  |  |  |  | H | [6 empty] | Shaft Prep | [5 empty] | Elevator Cabs | [5 empty] | Certification | bar: 7 to 8
1 | Remove Reshores, Floor Prep & Wall Layout | [47 empty] | H |  | Erect Stair 1 |  |  | H |  | Erect Stair 2 | [18 empty] | 9: Comeback Areas for Elev
2 | Fire Sprinkler & Install Walls | [47 empty] | H |  |  |  |  | H |  | Pour 1 |  |  |  | Pour 2
3 | OH Mechanical Duct | [47 empty] | H |  |  |  |  | H
4 | OH Mech Equip, Piping, Branch Lines & Plumbing | [47 empty] | H |  |  |  |  | H
5 | OH Electrical & Frame Walls | [47 empty] | H |  |  |  |  | H | [20 empty] | 9: Pre-functional Checklists; 10: B
6 | Frame Walls, Install In-wall Electrical & Plumbing | [47 empty] | H |  |  |  |  | H | [20 empty] | 13: Controls
7 | In-wall Process Piping, 1st Drywall, Insulation & Insp | [43 empty] | WEST A | A | A | B | H | B | B | C | C | H | D | D | E | E | [25 empty] | TAB
8 | Finish Walls & Painting | [45 empty] | WEST B | A | H | A | B | B | B | H | C | C | D | D | E | E | [25 empty] | Cx + FA Testing
9 | Painting & Install Ceiling Grid | [48 empty] | EAST A | A | A | B | H | B | B | C | C | D | D | E | E | [23 empty] | LS/ FA Testing
10 | Install Electrical Fixtures & Mech Ceiling Drops | [47 empty] | H |  |  | EAST B | A | H | A | B | B | B | C | C | D | D | E | E | [23 empty] | Functional Performance Testing
11 | Remaining Ceiling Drops & Install Casework | [47 empty] | H | [5 empty] | NORTH A | A | A | B | B | B | C | C | D | D | E | E
12 | Countertops, Millwork & Final Paint | [47 empty] | H |  |  |  |  | H |  |  | NORTH B | A | A | B | B | B | C | C | D | D | E | E
13 | Wall & Casework Fixtures, Ceiling Tiles & Flooring | [47 empty] | H |  |  |  |  | H |  |  |  |  | SOUTH A | A | A | B | B | B | C | C | D | D | E | E
14 | Flooring, Final Paint & 1st Clean | [47 empty] | H |  |  |  |  | H | [6 empty] | SOUTH B | A | A | B | B | B | C | C | D | D | E | E
15 | Punchlist, Corrections & Final Clean | [47 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H |  |  |  |  | Roofing Area A | [13 empty] | F | F | F | F | F
[49 empty] | H |  |  |  |  | H | [7 empty] | H E E E D C B B A: Roofing Area B
[49 empty] | H |  |  |  |  | H
FINISHING SITEWORK LEGEND | [48 empty] | H |  |  |  |  | H | [7 empty] | H E E E E D C B A: Set AHU
1 | Site Demoblization | [47 empty] | H |  |  |  |  | H | [7 empty] | H E E E E E D C B: Mechanical Installation
2 | UG Electrical | [47 empty] | H |  |  |  |  | H | [12 empty] | Controls | [9 empty] | AREA A | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
3 | Rough Grading | [47 empty] | H |  |  |  |  | H | [14 empty] | Point to Point | [8 empty] | AREA B | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
4 | Hardscaping | [47 empty] | H |  |  |  |  | H | [15 empty] | Mech Startup | [8 empty] | AREA C | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | B
5 | Trees & Irrigation | [47 empty] | H |  |  |  |  | H
6 | Landscaping | [47 empty] | H |  |  |  |  | H
7 | Paving
8 | Site Finishes
Exteriors
Interiors
Structure
Sitework
Foundations
Neuroscience Institute Takt Plan
POWER ON
AIR ON

## Full MACRO - After Review
|  |  | 2022 | [51 empty] | 2023 | [51 empty] | 2024
|  |  | Cold Winter Months | [21 empty] | Hot Summer Months | [21 empty] | Cold Winter Months | [29 empty] | Hot Summer Months | [21 empty] | Cold Winter Months
|  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY
|  |  | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 1900-01-23 | 1899-12-31 | 1900-01-07 | 15 | 22 | 29
|  | MILESTONES | [35 empty] | Exteriors Phase Pull Plan
[24 empty] | Sitework Complete | [10 empty] | Foundation Complete | [16 empty] | Structure complete | [10 empty] | Dry-in | [7 empty] | Air On |  |  |  |  | Final Sitework Pull Plan | [7 empty] | Interior Complete
[29 empty] | Structure Phase Pull Plan | [16 empty] | Interiors Phase Pull Plan | [20 empty] | Power On | [5 empty] | Exterior Complete
|  | PROCUREMENT | [30 empty] | Electrical Gear | [22 empty] | B | B | B | SES Fit-out & Energize
[32 empty] | HVAC Equipment | [27 empty] | B | B | B
[25 empty] | Windows | [26 empty] | B | B | B | B
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[9 empty] | Entire Site | MOB |  | 1H | 1H | 1H | 1I | 1I | 1I | 1I | 1J | 1J | 1J | 1J | 1K | [25 empty] | H |  |  |  |  | H
BEGINNING SITEWORK WORK | [22 empty] | ZONE A | F1 | F1 | F2 | F2 | F3 | F3 | F4 | F4 | F4 | B | B | [14 empty] | H |  |  |  |  | H
1H | Excavation/Grading | [23 empty] | ZONE B | F1 | F1 | F2 | F2 | F3 | F3 | F4 | F4 | F4 | B | B | [12 empty] | H |  |  |  |  | H
1I | Install Storm/Sanitary/Water/Dry U.G. Utilities | [47 empty] | H |  |  |  |  | H
1J | Parking Area Base Stone | [47 empty] | H |  |  |  |  | H
1K | Final Grading | [7 empty] | NTP | [24 empty] | LEVEL 1 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S3 | S3 | S4 | S4 | S4 |  | H |  |  |  |  | H | [33 empty] | Substantial Completion |  |  |  | Final Completion + Financial Completion
[35 empty] | LEVEL 2 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S3 | S3 | S4 | S4 | S4 | H |  |  |  |  | H
[36 empty] | LEVEL 3 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S3 | S3 | S4 | S4 | H | S4 |  |  |  | H
[37 empty] | LEVEL 4 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S3 | S3 | S4 | H | S4 | S4 |  |  | H
FOUNDATION LEGEND | [37 empty] | LEVEL 5 | S1 | S1 | S1 | S1 | S2 | S2 | S2 | S2 | S3 | S3 | H | S4 | S4 | S4 |  | H
F1 | Excavate & Pour Footings | [47 empty] | H |  |  |  |  | H
F2 | Columns & Walls | [47 empty] | H |  |  |  |  | H
F3 | UG MEP | [47 empty] | H |  |  |  |  | H
F4 | SOG | [47 empty] | H |  |  |  |  | H
B | Buffer | [47 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H
[49 empty] | FLOOR 1 |  |  | ZONE 1A | 1 | H | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
STRUCTURE LEGEND | [48 empty] | H |  |  |  | ZONE 1B | H | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
S1 | Deck Formwork | [47 empty] | H |  |  |  |  | H
S2 | Deck MEP & Reinforcing | [47 empty] | H |  |  | FLOOR 2 |  |  | ZONE 2A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
S3 | Deck Inspections & Place | [47 empty] | H |  |  |  |  | H |  | ZONE 2B | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
S4 | Columns & Walls | [47 empty] | H |  |  |  |  | H |  |  | ZONE 2C | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H |  |  |  | ZONE 2D | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H |  |  |  |  | ZONE 2E | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H |  |  | FLOOR 3 |  |  | ZONE 3A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
EXTERIOR LEGEND | [48 empty] | H |  |  |  |  | H | [6 empty] | ZONE 3B | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
A | Structural Steel Supports | [47 empty] | H |  |  |  |  | H | [7 empty] | ZONE 3C | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
B | Framing & Sheathing | [47 empty] | H |  |  |  |  | H
C | EIFS | [47 empty] | H |  |  |  |  | H | [5 empty] | FLOOR 4 |  |  | ZONE 4A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
D | Window Installation | [47 empty] | H |  |  |  |  | H | [9 empty] | ZONE 4B | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
E | Final Caulking & Finishes | [47 empty] | H |  |  |  |  | H | [10 empty] | ZONE 4C | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
F | Shade Structure | [47 empty] | H |  |  |  |  | H | [11 empty] | ZONE 4D | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[49 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H | [9 empty] | FLOOR 5 |  |  | ZONE 5A | 1 | 2 | 3 | 4 | 5 | 6 | B | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | B
[49 empty] | H |  |  |  |  | H
INTERIOR LEGEND | [48 empty] | H |  |  |  |  | H | [6 empty] | Shaft Prep | [5 empty] | Elevator Cabs | [5 empty] | Certification | bar: 7 to 8
1 | Remove Reshores, Floor Prep & Wall Layout | [47 empty] | H |  | Erect Stair 1 |  |  | H |  | Erect Stair 2 | [18 empty] | 9: Comeback Areas for Elev
2 | Fire Sprinkler & Install Walls | [47 empty] | H |  |  |  |  | H |  | Pour 1 |  |  |  | Pour 2
3 | OH Mechanical Duct | [47 empty] | H |  |  |  |  | H
4 | OH Mech Equip, Piping, Branch Lines & Plumbing | [47 empty] | H |  |  |  |  | H
5 | OH Electrical & Frame Walls | [47 empty] | H |  |  |  |  | H | [20 empty] | 9: Pre-functional Checklists; 10: B
6 | Frame Walls, Install In-wall Electrical & Plumbing | [47 empty] | H |  |  |  |  | H | [20 empty] | 13: Controls
7 | In-wall Process Piping, 1st Drywall, Insulation & Insp | [43 empty] | EAST A | A | A | B | H | B | B | C | C | H | D | D | E | E | [25 empty] | TAB
8 | Finish Walls & Painting | [45 empty] | EAST B | A | H | A | B | B | B | H | C | C | D | D | E | E | [25 empty] | Cx + FA Testing
9 | Painting & Install Ceiling Grid | [48 empty] | SOUTH A | A | A | B | H | B | B | C | C | D | D | E | E | [23 empty] | LS/ FA Testing
10 | Install Electrical Fixtures & Mech Ceiling Drops | [47 empty] | H |  |  | SOUTH B | A | H | A | B | B | B | C | C | D | D | E | E | [23 empty] | Functional Performance Testing
11 | Remaining Ceiling Drops & Install Casework | [47 empty] | H | [5 empty] | WEST A | A | A | B | B | B | C | C | D | D | E | E
12 | Countertops, Millwork & Final Paint | [47 empty] | H |  |  |  |  | H |  |  | WEST B | A | A | B | B | B | C | C | D | D | E | E
13 | Wall & Casework Fixtures, Ceiling Tiles & Flooring | [47 empty] | H |  |  |  |  | H |  |  |  |  | NORTH A | A | A | B | B | B | C | C | D | D | E | E
14 | Flooring, Final Paint & 1st Clean | [47 empty] | H |  |  |  |  | H | [6 empty] | NORTH B | A | A | B | B | B | C | C | D | D | E | E
15 | Punchlist, Corrections & Final Clean | [47 empty] | H |  |  |  |  | H
[49 empty] | H |  |  |  |  | H |  |  |  |  | Roofing Area A | [13 empty] | F | F | F | F | F
[49 empty] | H |  |  |  |  | H | [7 empty] | H E E E D C B B A: Roofing Area B
[49 empty] | H |  |  |  |  | H
FINISHING SITEWORK LEGEND | [48 empty] | H |  |  |  |  | H | [7 empty] | H E E E E D C B A: Set AHU
1 | Site Demoblization | [47 empty] | H |  |  |  |  | H | [7 empty] | H E E E E E D C B: Mechanical Installation
2 | UG Electrical | [47 empty] | H |  |  |  |  | H | [12 empty] | Controls | [9 empty] | AREA A | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
3 | Rough Grading | [47 empty] | H |  |  |  |  | H | [14 empty] | Point to Point | [8 empty] | AREA B | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
4 | Hardscaping | [47 empty] | H |  |  |  |  | H | [15 empty] | Mech Startup | [8 empty] | AREA C | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | B
5 | Trees & Irrigation | [47 empty] | H |  |  |  |  | H
6 | Landscaping | [47 empty] | H |  |  |  |  | H
7 | Paving
8 | Site Finishes
Exteriors
Interiors
Structure
Sitework
Foundations
Neuroscience Institute Takt Plan
POWER ON
AIR ON
Floor 5 interiors
Floor 4 interiors
Floor 3 interiors
Floor 2 interiors
Floor 1 interiors

## One Floor Macro Example
[16 empty] | 2022 | [38 empty] | 2023 | [34 empty] | 2024 | [52 empty] | 2025 | [51 empty] | 2026 | [51 empty] | 2027
[47 empty] | Cold Winter Months | [42 empty] | Cold Winter Months | [43 empty] | Cold Winter Months | [51 empty] | Cold Winter Months | [51 empty] | Cold Winter Months | [51 empty] | Cold Winter Months
[16 empty] | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
[16 empty] | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | time axis 2024-01-01 to 2027-12-27
[34 empty] | # Weeks |  |  | Description |  |  |  | Long Lead Procurment
[36 empty] | 14 | Kitchens | [33 empty] | D | D | B
[16 empty] | 1 | Remove re-shores & Final patch ceiling | [18 empty] | 8 | Cabinets | [32 empty] | D | D | D
[16 empty] | 2 | Floor prep & Wall layout | [18 empty] | 20 | Light Fixtures | [32 empty] | D
[16 empty] | 3 | Sprinkler main and branch lines
[16 empty] | 4 | Priority walls & Install OH mecanical duct
[16 empty] | 5 | Install OH mechanical duct | [65 empty] | SUBSTANTIAL COMPLETION
[16 empty] | 6 | Install OH mechanical equipment & piping
[16 empty] | 7 | Install OH mechanical branch lines & OH plumbing | [37 empty] | Zone 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
[16 empty] | 8 | OH electrical | [38 empty] | Zone 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
[16 empty] | 9 | Frame walls | [39 empty] | Zone 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
[16 empty] | 10 | In-wall electrical & Plumbing | [39 empty] | 15 14 13: Power on; 21 20 19: Air on
[16 empty] | 11 | In-wall process piping & One-side drywall
[16 empty] | 12 | In-wall inspections & Place insulation
[16 empty] | 13 | Finish walls
[16 empty] | 14 | Painting 1st & 2nd coat
[16 empty] | 15 | Ceiling grid
[16 empty] | 16 | Electrical fixtures
[16 empty] | 17 | Electrical fixtures, Install mech ceiling & remaining drops
[16 empty] | 18 | Casework
[16 empty] | 19 | Casework & Countertops
[16 empty] | 20 | Millwork & Final paint
[16 empty] | 21 | Wall and casework fixtures & Ceiling tiles
[16 empty] | 22 | Flooring
[16 empty] | 23 | Final paint & First Clean
[16 empty] | 24 | Worklist & Punchlist
[16 empty] | 25 | Corrections & Final clean
This steps are also processed in miro, you can find a template in the next link:
https://miro.com/app/board/uXjVOj11FK4=/?share_link_id=422339222032
Try to remain in the Macro Range from the middle to the bottom
[34 empty] | # Weeks |  |  | Description |  |  |  | Long Lead Procurment | bar: 2 1 Zone 3 to 22 21 20
[36 empty] | 14 | Kitchens | bar: 2 1 Zone 3 to 10 9 8
[36 empty] | 8 | Cabinets | bar: 2 1 Zone 3 to 9 8 7
[36 empty] | 20 | Light Fixtures | bar: 2 1 Zone 3 to 7 6 5
[55 empty] | JANUARY |  | 5 4 3: FEBRUARY; 9 8 7: MARCH; 13 12 11: APRIL; 17 16 15: MAY; 22 21 20: JUNE; 25 25 24: JULY
[35 empty] | 1 | Remove re-shores, Floor Prep & Wall Layout | [20 empty] | 20 19 18: SUBSTANTIAL COMPLETION | ORIGINAL SUBSTANTIAL COMPLETION
[35 empty] | 2 | Fire Sprinkler & Install Walls | [18 empty] | Zone 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 3 | OH Mechanical Duct | [19 empty] | Zone 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 4 | OH Mech Equip, Piping, Branch Lines & Plumbing | [20 empty] | Zone 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 5 | OH Electrical & Frame Walls | [21 empty] | Zone 4 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 6 | Frame Walls, Install In-wall Electrical & Plumbing | [22 empty] | Zone 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[35 empty] | 7 | In-wall Process Piping, 1st Drywall, Insulation & Insp | [22 empty] | 7 6 5 4 3: Power on; 11 10 9 8 7: Air on
[35 empty] | 8 | Finish Walls & Painting
[35 empty] | 9 | Painting & Install Ceiling Grid
[35 empty] | 10 | Install Electrical Fixtures & Mech Ceiling Drops
[35 empty] | 11 | Remaining Ceiling Drops & Install Casework
[35 empty] | 12 | Countertops, Millwork & Final Paint
[35 empty] | 13 | Walls & Casework Fixtures, Ceiling Tiles & Flooring
[35 empty] | 14 | Flooring, Final Paint & 1st Clean
[35 empty] | 15 | Punchlist, Corrections & Final Clean
JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY
Zone 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
| Zone 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  | Zone 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Zone 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9
[5 empty] | Zone 2 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7
[10 empty] | Zone 3 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5
[15 empty] | Zone 4 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4
[20 empty] | Zone 5 | 1 | 1 | 1 | 2 | 2
JANUARY |  | FEBRUARY 5 4 3: FEBRUARY; MARCH 9 8 7: MARCH; APRIL 13 12 11: APRIL; MAY 17 16 15: MAY; JUNE 22 21 20: JUNE; JUNE 25 25 24: JULY
Zone 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Zone 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  | Zone 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  | Zone 4 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  |  | Zone 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Start Here
Interiors
Interiors
Optimizing Takt Plan in the Macro Level
4 Week Look Ahead
Zone Map
Interiors Legend
Zone Map
Interiors Legend
Scan QR Code Below With Smart Phone Camera
Buffer
Rules of Thumb:
1. Check the plan with your calculator
2. Check the shape
3. Check for conservative or aggressive packaging
4. Check for the balance between divisions and additions
1
2
3
4
Buffers
Step 1: Check Rules of Thumb
1
Step 2: Optimization
2
Step 3: Repackage
3
Step 4: Map Out The Optimized Takt Plan Including Buffers
4
Steps Summary:

## Buyout & Procurement Log
[34 empty] | Today: | 46238
[34 empty] | Week of the year: | 32
Spec Section | Takt Zone | Scope of Work | Selected Subcontractor | RFP To Subcontractor | RFI & PREQ. Prep WKS | RFI & PREQ. Due | RFI Due To Sub Visit Start WKS | Start Trade Partner Site Visit | Trade Visit Start To Bids due WKS | Bids Due | Bid Review WKS | Client Presentation & Sub Selection | Approvals & NTP WKS | Start Contracting with Sub | Contracting Process Time (WKS) | Drop Dead Subcontract Execution | Subcontract Executed | Submittal Prep WKS | Receive Submittal | Actual Approved Submittal | Submittal Review WKS | Sent To Design Team | Design Approved | Design Team Approval Wks. | Release Date (Order Materials By) | Confirmed Release Date | Submittal Over/Under Days | Lead Time WKS | Ship Date | Delivery Weeks | Buffer Duration WEEKS | Actual Date on Site | Required On Job (Get Superintendent Input!) | Material Over/Under DAYS | Notes | Last Date of Contact
Toggle Light Switches | 2 | Electrical | Electrical Services | 2023-07-27 | 1 | 2023-08-03 | 1 | 2023-08-10 | 1 | 2023-08-17 | 1 | 2023-08-24 | 1 | 2023-08-31 | 1 | 2023-09-07 |  | 1 | 2023-09-14 |  | 1 | 2023-09-21 |  | 1 | 2023-09-28 |  |  | 5 | 2023-11-02 | 1 | 1 |  | 2023-11-16
Duplex Receptacles | 2 | Electrical | Electrical Services | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 | 0 | 2024-10-12 |  | 0 | 2024-10-12 |  | 0 | 2024-10-12 |  | 0 | 2024-10-12 |  |  | 3 | 2024-11-02 | 2 | 0 |  | 2024-11-16
Recessed lighting | 2 | Electrical | Electrical Services | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 | 0 | 2024-09-14 |  | 0 | 2024-09-14 |  | 0 | 2024-09-14 |  | 0 | 2024-09-14 |  |  | 5 | 2024-10-19 | 2 | 2 |  | 2024-11-16
Cabinets | 2 | Casework | Cabintes & More LLC | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 |  | 0 | 2024-08-01 |  | 0 | 2024-08-01 |  | 0 | 2024-08-01 |  |  | 14 | 2024-11-07 | 3 | 0 |  | 2024-11-28
Drawers | 2 | Casework | Cabintes & More LLC | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 0 | 2024-10-10 | 2023-12-30 | 0 | 2024-10-10 |  | 0 | 2024-10-10 |  | 0 | 2024-10-10 |  | -285 | 4 | 2024-11-07 | 2 | 1 |  | 2024-11-28
Bookshelves | 2 | Casework | Cabintes & More LLC | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 | 0 | 2024-10-03 |  | 0 | 2024-10-03 |  | 0 | 2024-10-03 |  | 0 | 2024-10-03 |  |  | 7 | 2024-11-21 | 1 | 0 |  | 2024-11-28
Windows | 2 | Millwork | Doors & Windows Inc | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 | 0 | 2024-08-30 |  | 0 | 2024-08-30 |  | 0 | 2024-08-30 |  | 0 | 2024-08-30 |  |  | 8 | 2024-10-25 | 5 | 1 |  | 2024-12-06
Doors | 2 | Millwork | Doors & Windows Inc | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 | 0 | 2024-10-11 |  | 0 | 2024-10-11 |  | 0 | 2024-10-11 |  | 0 | 2024-10-11 |  |  | 4 | 2024-11-08 | 3 | 1 |  | 2024-12-06
Light Fixtures | 2 | Electrical | Electrical Services | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 | 0 | 2024-06-22 |  | 0 | 2024-06-22 |  | 0 | 2024-06-22 |  | 0 | 2024-06-22 |  |  | 20 | 2024-11-09 | 1 | 0 |  | 2024-11-16
Electric Sockets | 2 | Electrical | Electrical Services | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  |  | 3 | 2024-10-26 | 2 | 1 |  | 2024-11-16
Security Alarm System | 2 | Electrical | Electrical Services | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 | 0 | 2024-10-19 |  | 0 | 2024-10-19 |  | 0 | 2024-10-19 |  | 0 | 2024-10-19 |  |  | 2 | 2024-11-02 | 2 | 0 |  | 2024-11-16
Fire Alarm | 2 | Electrical | Electrical Services | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  | 0 | 2024-10-05 |  |  | 2 | 2024-10-19 | 2 | 2 |  | 2024-11-16
Kitchens | 2 | Casework | Kitchens Inc | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 0 | 2024-08-31 | 2023-12-30 | 0 | 2024-08-31 |  | 0 | 2024-08-31 |  | 0 | 2024-08-31 |  | -245 | 10 | 2024-11-09 | 2 | 1 |  | 2024-11-30
|  |  |  | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 | 0 | 2025-02-21 |  | 29 | 2025-09-12 |  | 2 | 2025-09-26 |  | 10 | 2025-12-05 |  |  | 0 | 2025-12-05 | 1 | 0 |  | 2025-12-12
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0
**ITEMS IN RED ARE IN TROUBLE** | [34 empty] | LAST DATE REVIEWED W/ SUPER:
Formulas:
RFP To Subcontractor = IF([RFI & PREQ. Due]="","",[RFI & PREQ. Due]-(7*[RFI & PREQ. Prep WKS]))
RFI & PREQ. Due = IF([Start Trade Partner Site Visit]="","",[Start Trade Partner Site Visit]-(7*[RFI Due To Sub Visit Start WKS]))
Start Trade Partner Site Visit = IF([Bids Due]="","",[Bids Due]-(7*[Trade Visit Start To Bids due WKS]))
Bids Due = IF([Client Presentation & Sub Selection]="","",[Client Presentation & Sub Selection]-(7*[Bid Review WKS]))
Client Presentation & Sub Selection = IF([Start Contracting with Sub]="","",[Start Contracting with Sub]-(7*[Approvals & NTP WKS]))
Start Contracting with Sub = IF([Drop Dead Subcontract Execution]="","",[Drop Dead Subcontract Execution]-(7*[Contracting Process Time (WKS)]))
Drop Dead Subcontract Execution = IF([Receive Submittal]="","",[Receive Submittal]-(7*[Submittal Prep WKS]))
Receive Submittal = IF([Sent To Design Team]="","",[Sent To Design Team]-([Submittal Review WKS]*7))
Sent To Design Team = IF([Release Date (Order Materials By)]="","",[Release Date (Order Materials By)]-([Design Team Approval Wks.]*7))
Release Date (Order Materials By) = IF([Ship Date]="","",[Ship Date]-(7*[Lead Time WKS]))
Ship Date = IF(AJ6="","",AJ6-(7*[Delivery Weeks])-(7*[Buffer Duration WEEKS]))
1
2
3
7
1
3
2
1
2
3
7
How to use Procurement Log:
1. Fill in the Spec Section, Scope of Work, Takt Zone and Trade Partner.
2. Start with the "Required on Job" date (you can obtain this from the norm-level takt plan).
3. Fill in the estimated delivery weeks and if considered, the buffer weeks.
4. Ship Dates will be updated automatically.
5. Add the Lead Time Weeks. (Required Submittal Approval will update automatically).
6. Fill in addtional work weeks such as Submittal Prep & Review WKS and "Design Team Approval WKS.
7. When the actual Released TP and Approved Submittal date is obtained, it is necesasay to fill it in manually.
NOTES: Only the "Required on Job" date is necessary to fill in, the other dates will update according the added information. Comment section can be used for special considerations or additional conditions for the log entry.
Information Needed
Automatically
BUYOUT
PROCUREMENT
Date is 1 to 14 days ahead
Date is 15+ days ahead
Date is today or past
Conditional Formatting Legend

## HIDDEN GRAPHICS (hidden)
Percentage | Scale
10% | 1
20% | 1
30% | 1
40% | 1
50% | 1
60% | 1
70% | 1
80% | 1
90% | 1
100% | 9
#REF!
Degrees | #REF!
| X | Y
Start | 0 | 0
Finish | #REF! | #REF!
Percentage | Scale
10% | 1
20% | 1
30% | 1
40% | 1
50% | 1
60% | 1
70% | 1
80% | 1
90% | 1
100% | 9
#REF!
Degrees | #REF!
| X | Y
Start | 0 | 0
Finish | #REF! | #REF!
|  |  | TOTAL END BUFFERS | #REF!
Percentage | Scale
10% | 1
20% | 1
30% | 1
40% | 1
50% | 1
60% | 1
70% | 1
80% | 1
90% | 1
100% | 9
#REF!
Degrees | #REF!
| X | Y
Start | 0 | 0
Finish | #REF! | #REF!
#REF!
KPIs
#REF!
#REF!