## Sheet1
Trade Partner Grading Criteria: | TP1 |  |  | TP2 |  | TP3 |  | TP4 |  | TP5 |  | TP6 |  | TP7
| B | 82.86% |  | B | 82.86% | B | 82.86% | B | 82.86% | B | 82.86% | B | 82.86% | B | 82.86%
Have you had to be reminded to clean your own areas of the project? | no | 100% |  | no | 100% | no | 100% | no | 100% | no | 100% | no | 100% | no | 100%
Clean score for the week? | 80 | 80% |  | 80 | 80% | 80 | 80% | 80 | 80% | 80 | 80% | 80 | 80% | 80 | 80%
Have you impacted the Campus or neighbors negatively? | No | 100% |  | No | 100% | No | 100% | No | 100% | No | 100% | No | 100% | No | 100%
Do all your crews have safety plans, JHAs, and PTPs for daily work? Turned in? | Yes | 100% |  | Yes | 100% | Yes | 100% | Yes | 100% | Yes | 100% | Yes | 100% | Yes | 100%
Are Foremen and Workers ontime for huddles? | Yes | 100% |  | Yes | 100% | Yes | 100% | Yes | 100% | Yes | 100% | Yes | 100% | Yes | 100%
Are deliveries scheduled, coordinated with general contractor, and on time? | No | 0% |  | No | 0% | No | 0% | No | 0% | No | 0% | No | 0% | No | 0%
Are materials and manpower ready for commitments this week? | Yes | 100% |  | Yes | 100% | Yes | 100% | Yes | 100% | Yes | 100% | Yes | 100% | Yes | 100%
General Contractor Grading Criteria:
| A | 62.5% | Comments:
Bathrooms decent and well maintained for Craft | Yes | 100%
Adequate lunch area provided for Craft | No | 0%
General Contractor responds quickly to requested safety needs? | Yes | 100%
The plan for the week and day is clearly identified and easy to follow? | No | 0%
General Contractor tries to reduce variation and impacts as much as possible? | Yes | 100%
Site is clean and organized? | No | 0%
Deliveries and material access are planned for and enforced? | Yes | 100%
Site is visually managed well for all workers? | Yes | 100%
General Contractor helps me and my company succeed? | Yes | 100%